## SCB-CP
S.No. | WBS | SO | Qty | Equipment Name | scope | Planner | Zero Date | CDD | Equipment Weight in KG | Manufacturing Planned Hours |  |  |  |  | Manufacturing Utilization Hours |  |  |  |  | Available Capacity SCB |  |  |  |  | Actual Capacity SCB | [6 empty] | Actual Welding | [14 empty] | Actual Milling Machining | [14 empty] | Actual CNC Lathe Machining | [14 empty] | Actual Assembly
[10 empty] | Welding | Milling Machining | CNC Lathe Machining | Assembly | Total Hours | Welding | Milling Machining | CNC Lathe Machining | Assembly | Total Hours | Welding | Milling Machining | CNC Lathe Machining | Assembly | Total Hours | Welding | Milling Machining | CNC Lathe Machining | Assembly | Total Hours | Order | Category | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | Total | Order | Category | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | Total | Order | Category | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | Total | Order | Category | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | Total | Diff-FAB | Diff-MILL | Diff-LATHE | Diff-ASS
1 | C00450X010.99.1000 |  |  | Turret Base | NA | AVIJIT SAHA | 2022-04-20 | 2022-11-30 | 9700 | 1308 | 125 |  |  | 1433 | 2295.14 | 64 | 57.2 |  | 2416.34 | -987.14 | 61 | -57.2 | 0 | -983.34 | 0 | 0 | 0 | 0 | 0 | Contract | DIRECT | [12 empty] | 0 | Contract | DIRECT | [12 empty] | 0 | Contract | DIRECT | [12 empty] | 0 | Contract | DIRECT | [12 empty] | 0 | -987.14 | 61 | -57.2 | 0
2 | C00525X010.1000 |  |  | LADLE TURRET WEDGE TYPE 1 | NA | AVIJIT SAHA | 2022-09-01 | 2022-09-30 |  | 300 |  |  |  | 300 | 4 | 73.8 |  |  | 77.8 | 296 | -73.8 | 0 | 0 | 222.2 | 0 | 0 | 0 | 0 | 0 | Contract | DIRECT | [12 empty] | 0 | Contract | DIRECT | [12 empty] | 0 | Contract | DIRECT | [12 empty] | 0 | Contract | DIRECT | [12 empty] | 0 | 296 | -73.8 | 0 | 0
3 | A03394M220.20.10.10P1000 | WBS |  | Converter vessel | NA | KRISHNASIS | 2023-05-08 | 2024-03-30 | 22000 | 8000 | 54 |  |  | 8054 | 7108.64 | 52 | 102.9 |  | 7263.54 | 891.36 | 2 | -102.9 | 0 | 790.46 | 407 | 0 | 0 | 0 | 407 | OTH | WBS | 407 | [11 empty] | 407 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | 484.36 | 2 | -102.9 | 0
4 | A03520M220.20.20P0110 | WBS |  | Blowing lance body | NA | Kameshwaran | 2024-05-15 |  | 5000 | 1024 |  | 55 |  | 1079 | 1391 | 8.5 |  |  | 1399.5 | -367 | -8.5 | 55 | 0 | -320.5 | 0 | 0 | 0 | 0 | 0 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | -367 | -8.5 | 55 | 0
5 | A03520M220.85P1000 | WBS |  | operational change parts oxygen lance |  | Kameshwaran | 2024-05-15 |  | 5000 | 1024 | 55 |  |  | 1079 | 1497 |  | 5 |  | 1502 | -473 | 55 | -5 | 0 | -423 | 200 | 55 | 0 | 0 | 255 | OTH | WBS | 200 | [11 empty] | 200 | OTH | WBS | 55 | [11 empty] | 55 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | -673 | 0 | -5 | 0
6 | A03520M220.40.10.50P1010 | WBS |  | Electrode Arms - PCA | NA only ass | Ravi Ranjan |  | 2024-12-31 | 15890 | 5960 | 280 | 150 | 300 | 6690 | 8422 | 474.2 | 303 |  | 9199.2 | -2462 | -194.2 | -153 | 300 | -2509.2 | 0 | 0 | 0 | 0 | 0 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | -2462 | -194.2 | -153 | 300
7 | A03520M220.86.30P0100 | WBS |  | Electrode Clamp Assbly-Spare | NA only ass | Ravi Ranjan |  | 2024-12-31 | 732 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | 0 | 0 | 0 | 0
8 | A03520M220.86.30P0200 | WBS |  | Contact Pad- Spare | NA | Ravi Ranjan |  | 2024-12-31 | 236 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | 0 | 0 | 0 | 0
9 | A03508M120.10.12P3000 A03508M120.96.01P2000 | WBS |  | TUYERE STOCK (MAIN -24+SPARE -5) MOUNTING JIG REFRACTORY JIG DOWNLEG & ELBOW-BLOWPIPE DISMANTLING DEVICE | NA | Ravi Ranjan | 2024-06-20 | 2025-03-20 | 60000 | 6000 | 172 |  |  | 6172 | 8267.67 | 24 | 231 | 7 | 8529.67 | -2267.67 | 148 | -231 | -7 | -2357.67 | 0 | 0 | 0 | 0 | 0 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | -2267.67 | 148 | -231 | -7
10 | ET560067341 | 72003581 |  | FINAL MACHINING & ASSEMBLY OF WORK ROLL CHOCKS - 2 SETS | NA | Ravi Ranjan | 2022-07-06 | 2023-04-10 |  |  | 450 |  | 200 | 650 | 204 | 1462.8 | 133.4 | 838 | 2638.2 | -204 | -1012.8 | -133.4 | -638 | -1988.2 | 0 | 0 | 0 | 0 | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | -204 | -1012.8 | -133.4 | -638
11 | ET560065841 | 72003480 |  | Mandrel Spares | NA | Ravi Ranjan | 2022-05-06 | 2025-10-19 | [5 empty] | 0 |  |  | 3 | 1000 | 1003 | 0 | 0 | -3 | -1000 | -1003 | 0 | 0 | 0 | 0 | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | 0 | 0 | -3 | -1000
12 | ET560076197 | 72004059 |  | Mandrel Spares -Segments | NA | Ravi Ranjan | 2022-12-30 | 2025-10-19 | [9 empty] | 520 | 520 | 0 | 0 | 0 | -520 | -520 | 0 | 0 | 0 | 0 | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | 0 | 0 | 0 | -520
13 | ET430084421 | 72004601 |  | FIXED HOOD LD2 |  | Rejeesh | 2024-04-12 | 2025-04-30 | 35000 | 8000 |  | 30 |  | 8030 | 2311 |  |  |  | 2311 | 5689 | 0 | 30 | 0 | 5719 | 8689 | 0 | 30 | 0 | 8719 | OTH | SERVICE | 2173 | 2172 | 2172 | 2172 | [8 empty] | 8689 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | 30 | [11 empty] | 30 | OTH | SERVICE | [12 empty] | 0 | -3000 | 0 | 0 | 0
14 | ET430095286 | 72005231 |  | SEGMENT 9_14 | NA only ass | Amulya Jena | 2024-04-25 | 2025-04-30 | 60000 | 6652 | 1440 |  | 2500 | 10592 | 8434.45 | 777 | 597 | 12 | 9820.45 | -1782.45 | 663 | -597 | 2488 | 771.55 | 0 | 0 | 0 | 2488 | 2488 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE |  | 1244 | 1244 | [9 empty] | 2488 | -1782.45 | 663 | -597 | 0
15 | ET460096489 | 72005405 |  | COOLING STACK 1 to 5 & COVER | NA | Rejeesh | 2024-06-27 | 2025-06-08 | 40000 | 12000 |  | 330 |  | 12330 | 4616 |  |  |  | 4616 | 7384 | 0 | 330 | 0 | 7714 | 0 | 0 | 0 | 0 | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | 7384 | 0 | 330 | 0
16 | ET460096654 | 72005582 |  | EAF TILTING PLATFORM & SUBSTRUCTRES |  | Amulya Jena | 2024-09-23 | 2025-09-30 | 30000 | 9759.08 | 140 | 100 |  | 9999.08 |  |  |  |  | 0 | 9759.08 | 140 | 100 | 0 | 9999.08 | 9759 | 140 | 100 | 0 | 9999 | OTH | SERVICE | 3253 | 3253 | 3253 | [9 empty] | 9759 | OTH | SERVICE | 140 | [11 empty] | 140 | OTH | SERVICE | 100 | [11 empty] | 100 | OTH | SERVICE | [12 empty] | 0 | 0.08 | 0 | 0 | 0
17 | ET300093198 | 72005103 |  | Main cylinder with platten with bush | NA | SHASHIKUMAR | 2024-11-08 |  | 4000 | 1231 | 196 |  |  | 1427 | 1687.3 | 416.4 | 68.1 |  | 2171.8 | -456.3 | -220.4 | -68.1 | 0 | -744.8 | 0 | 0 | 0 | 0 | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | -456.3 | -220.4 | -68.1 | 0
18 | ET430096681 | 72005606 |  | MOLD OSCILLATION UNIT & MOLD CARRIER |  | Kameshwaran | 2024-09-27 | 2026-02-14 | 20000 | 3630 | 280 | 130 | 550 | 4590 | 4067.17 | 238.3 | 76.55 |  | 4382.02 | -437.17 | 41.7 | 53.45 | 550 | 207.98 | 0 | 42 | 53 | 550 | 645 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | 42 | [11 empty] | 42 | OTH | SERVICE | 53 | [11 empty] | 53 | OTH | SERVICE | 550 | [11 empty] | 550 | -437.17 | -0.3 | 0.45 | 0
19 | A03533M120.10.12P3000 A03533M120.80.01P3020 A03533M120.80.01P4000 | WBS | 52 | Tuyere Stock BF 2Yr Spare - Tuyere stock BF - Comm Spare - Tuyere stock | PANKAJ | Ravi Ranjan | 2024-07-19 | 2025-03-20 | 180000 | 16422 |  | 678 |  | 17100 | 10925 | 13 | 139.05 |  | 11077.05 | 5497 | -13 | 538.95 | 0 | 6022.95 | 5497 | 0 | 539 | 0 | 6036 | OTH | WBS | 1833 | 1832 | 1832 | [9 empty] | 5497 | OTH | WBS | [12 empty] | 0 | OTH | WBS | 539 | [11 empty] | 539 | OTH | WBS | [12 empty] | 0 | 0 | -13 | -0.05 | 0
20 | A03533M120.80.01P3005 | WBS |  | BF 2Yr Spare - Centering and Wear device | NA | SANGRAM SWAIN | 2024-05-17 | [6 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | 0 | 0 | 0 | 0
21 | A03520M220.20.70.44P0500 | WBS | 1 | INTERCONNECTING PIPING | NA | Kameshwaran | 2024-08-09 |  |  | 132 |  | 26 |  | 158 | 141 |  | 3 |  | 144 | -9 | 0 | 23 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | -9 | 0 | 23 | 0
22 | A03520M220.35.20.40P1100 | WBS | 2 | TEEMING LADLE TRANSFER CAR AT LF | NA | Ravi Ranjan | 2024-09-13 |  | 85000 | 5185 | 672 | 160 | 750 | 6767 | 5830.686 | 658.5 | 575.5 |  | 7064.686 | -645.686 | 13.5 | -415.5 | 750 | -297.686 | 0 | 0 | 0 | 750 | 750 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | OTH | WBS | 750 | [11 empty] | 750 | -645.686 | 13.5 | -415.5 | 0
23 | A03613M120.25P1500 | WBS | 1 | GOGGLE VALVE ND 1600 SLIDE TYPE |  | SANGRAM SWAIN | 2024-10-10 |  | 7000 | 2411.88 | 680 | 200 | 800 | 4091.88 | 3501.01 | 350.2 | 298 |  | 4149.21 | -1089.13 | 329.8 | -98 | 800 | -57.33 | 0 | 330 | 0 | 800 | 1130 | OTH | WBS | [12 empty] | 0 | OTH | WBS | 165 | 165 | [10 empty] | 330 | OTH | WBS | [12 empty] | 0 | OTH | WBS | 800 | [11 empty] | 800 | -1089.13 | -0.2 | -98 | 0
24 | A03613M120.25P1525 | WBS | 1 | COMBUSTION GAS ENRICHMENT GOGGLE VALVE DN 450 | NA | SANGRAM SWAIN | 2024-10-10 |  | 15000 | 1896 | 188 |  | 800 | 2884 | 919 | 169.6 | 207 |  | 1295.6 | 977 | 18.4 | -207 | 800 | 1588.4 | 0 | 0 | 0 | 0 | 0 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | 977 | 18.4 | -207 | 800
25 | 8564 | SO | 2 | TWIN LADLE FURNACE WATER COOLED ROOF | APEX | Rejeesh | 2024-11-27 |  | 14000 | 5732 | 80 |  |  | 5812 |  |  |  |  | 0 | 5732 | 80 | 0 | 0 | 5812 | 0 | 0 | 0 | 0 | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | 5732 | 80 | 0 | 0
26 | A03520M220.86.40P0200 | WBS |  | SPARES FOR LADLE TRANSFER CARS-GEARBOX,COUPLINGS,BRAKE,BEARING,DRIVE WHEEL ASSLY | NA | Ravi Ranjan | 2024-12-05 |  |  | 150 |  |  | 70 | 220 |  |  |  |  | 0 | 150 | 0 | 0 | 70 | 220 | 0 | 0 | 0 | 70 | 70 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | OTH | WBS |  |  | 70 | [9 empty] | 70 | 150 | 0 | 0 | 0
27 | S000611SMP.LSH.LAS.LAL1 S000611SMP.LSH.LAS.LAL2 S000611SMP.LSH.LAS.LAL3 S000611SMP.LSH.LAS.LAL4 S000611SMP.LSH.LAS.LAL5 S000611SMP.LSH.LAS.LAL6 | 9149 | 6 | STEEL TEEMING LADLE |  | KRISHNASIS | 2024-11-29 | 2025-11-30 | 300000 | 29215 | 420 |  |  | 29635 | 28222 | 376 | 371 | 591 | 29560 | 993 | 44 | -371 | -591 | 75 | 993 | 44 | 0 | 160 | 1197 | Contract | DIRECT | 496.5 | 496.5 | [10 empty] | 993 | Contract | DIRECT | 44 | [11 empty] | 44 | Contract | DIRECT | [12 empty] | 0 | Contract | DIRECT | 160 | [11 empty] | 160 | 0 | 0 | -371 | -751
28 | 9179 | SO | 2 | FINAL MACHINING OF EDGER HOUSING CASSETTE ASSEMBLY WITH LINERS | Sanad | SHASHIKUMAR | 2024-12-10 |  | 14000 | 28 | 400 |  | 150 | 578 |  |  |  |  | 0 | 28 | 400 | 0 | 150 | 578 | 0 | 0 | 0 | 0 | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | 28 | 400 | 0 | 150
29 | A03520M220.55.40.20P0100 | WBS | 1 | LADLE TILTER |  | AMULYA JENA | 2025-01-27 | 2025-11-30 | 30000 | 5120 | 280 |  | 200 | 5600 | 4485.02 | 141.7 | 73.5 |  | 4700.22 | 634.98 | 138.3 | -73.5 | 200 | 899.78 | 635 | 138 | 0 | 200 | 973 | OTH | WBS | 300 | 335 | [10 empty] | 635 | OTH | WBS | 138 | [11 empty] | 138 | OTH | WBS | [12 empty] | 0 | OTH | WBS | 200 | [11 empty] | 200 | -0.02 | 0.3 | -73.5 | 0
30 | S000348RML.FMA.URM.CHO S000348RML.FMA.EDM.CHO | 9227 | 3 | ROLL CHOCK ASSEMBLY UR/UF & EDGER | NA only ass | SHASHIKUMAR | 2025-01-30 | 2025-02-12 |  |  | 140 |  | 420 | 560 | 3.5 | 116.5 | 82.5 | 985 | 1187.5 | -3.5 | 23.5 | -82.5 | -565 | -627.5 | 0 | 0 | 0 | 0 | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | -3.5 | 23.5 | -82.5 | -565
31 | ET760096764 | 72005686 | 1 | SEGMENT 11 |  | Kameshwaran | 2025-01-31 | 2026-02-28 | 4784 | 3925 | 370 | 380 | 700 | 5375 | 3965.25 | 295.6 | 672.35 | 90 | 5023.2 | -40.25 | 74.4 | -292.35 | 610 | 351.8 | 0 | 74 | 0 | 610 | 684 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE |  | 74 | [10 empty] | 74 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | 610 | [11 empty] | 610 | -40.25 | 0.4 | -292.35 | 0
32 | 12301 | SO | 1 | SEGMENT 12 | NA | Kameshwaran | 2025-02-12 | 2026-01-16 | 14000 | 1450 | 405 |  | 700 | 2555 | 1489 | 1090 | 1243 | 872 | 4694 | -39 | -685 | -1243 | -172 | -2139 | 0 | 0 | 0 | 0 | 0 | Group | DIRECT | [12 empty] | 0 | Group | DIRECT | [12 empty] | 0 | Group | DIRECT | [12 empty] | 0 | Group | DIRECT | [12 empty] | 0 | -39 | -685 | -1243 | -172
33 | 13827 | SO | 2 | REFURBISHMENT OF DSITRIBUTION CHUITE | NA | SANGRAM SWAIN | 2025-03-26 | 2025-07-12 | 7420 | 168 | 128 |  | 480 | 776 | 14 | 15 | 23.7 | 747 | 799.7 | 154 | 113 | -23.7 | -267 | -23.7 | 0 | 0 | 0 | 0 | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | 154 | 113 | -23.7 | -267
34 | 11649 | SO | 3 | F1-F4 BUR CHANGE SLEDGE ASSEMBLY | NA | Kameshwaran | 2025-03-24 |  | 15469 |  |  |  |  | 0 | 27.5 | 660 | 98.3 | 1 | 786.8 | -27.5 | -660 | -98.3 | -1 | -786.8 | 0 | 0 | 0 | 0 | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | -27.5 | -660 | -98.3 | -1
35 | 14904 | SO | 1 | REFURBISHMENT OF DSITRIBUTION CHUTE MIDI L-3.6M | NA | SANGRAM SWAIN | 2025-04-17 | 2026-02-28 | 1631 | 84 | 64 |  | 240 | 388 |  |  |  | 238 | 238 | 84 | 64 | 0 | 2 | 150 | 0 | 0 | 0 | 0 | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | 84 | 64 | 0 | 2
36 | 15031 | SO | 6 | ECCENTRIC WHEL ASSEMBLY | NA | SHASHIKUMAR | 2025-04-30 | 2025-12-31 | 4728 |  |  |  | 300 | 300 |  |  |  |  | 0 | 0 | 0 | 0 | 300 | 300 | 0 | 0 | 0 | 0 | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | 0 | 0 | 0 | 300
37 | 15541 | SO | 5 | DOWNLEG ARRANGEMENT | NA | SANGRAM SWAIN | 2025-05-07 | 2025-12-31 | 5995 | 400 |  |  | 80 | 480 | 501 |  |  | 241 | 742 | -101 | 0 | 0 | -161 | -262 | 0 | 0 | 0 | 0 | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | -101 | 0 | 0 | -161
38 | 16262 | SO | 8 | CHASSIS FRAME | HOLD | AVIJIT SAHA | 2025-05-16 | 2025-10-31 | 7424 | 3910 | 160 |  |  | 4070 | 2243 | 25.33 | 89 | 35 | 2392.33 | 1667 | 134.67 | -89 | -35 | 1677.67 | 0 | 0 | 0 | 0 | 0 | Contract | DIRECT | [12 empty] | 0 | Contract | DIRECT | [12 empty] | 0 | Contract | DIRECT | [12 empty] | 0 | Contract | DIRECT | [12 empty] | 0 | 1667 | 134.67 | -89 | -35
39 | 15540 | SO | 7 | WEAR PLATES | NA | SANGRAM SWAIN | 2025-05-19 | 2025-11-27 | 2690 |  |  |  | 4 | 4 | 15 | 48 | 1.75 | 55 | 119.75 | -15 | -48 | -1.75 | -51 | -115.75 | 0 | 0 | 0 | 0 | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | -15 | -48 | -1.75 | -51
40 | 17368 | SO | 1 | SKIP CAR ASSEMBLY | NA only ass | SANGRAM SWAIN | 2025-06-17 | 2026-06-05 | 4310 | 1277 | 30 | 108 | 300 | 1715 | 1616 | 178 | 298 | 447 | 2539 | -339 | -148 | -190 | -147 | -824 | 0 | 0 | 0 | 0 | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | -339 | -148 | -190 | -147
41 | S000765DIP.DUX.DIX.DYX1 S000765DIP.DUX.DIX.DYX2 S000765DIP.DUX.DIX.DYX3 | 20140 | 12 | FRAMEWORK,CRUSHER,COMPLETE |  | AVIJIT SAHA | 2025-06-19 | 2026-04-20 | 100000 | 24257.1429 | 60 | 600 |  | 24917.1429 |  |  |  |  | 0 | 24257.1429 | 60 | 600 | 0 | 24917.1429 | 24257 | 60 | 600 | 0 | 24917 | Contract | DIRECT | 1757 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 |  |  | 24257 | Contract | DIRECT |  |  | 10 | 10 | 10 | 10 | 10 | 10 |  |  |  |  | 60 | Contract | DIRECT |  |  | 100 | 100 | 100 | 100 | 100 | 100 |  |  |  |  | 600 | Contract | DIRECT | [12 empty] | 0 | 0.14286 | 0 | 0 | 0
42 | 20143 | SO | 12 | SURFACE RECLAIM FEEDER | NA | AVIJIT SAHA | 2025-06-19 | 2026-04-30 | 12000 |  |  |  | 1800 | 1800 |  |  |  |  | 0 | 0 | 0 | 0 | 1800 | 1800 | 0 | 0 | 0 | 1800 | 1800 | Contract | DIRECT | [12 empty] | 0 | Contract | DIRECT | [12 empty] | 0 | Contract | DIRECT | [12 empty] | 0 | Contract | DIRECT |  |  |  |  | 300 | 300 | 300 | 300 | 300 | 300 |  |  | 1800 | 0 | 0 | 0 | 0
43 | A03607X01P1 | WBS |  | Cladded Rolls & Copper plates |  | AMAN SINGH | [7 empty] | 0 | 11271 | 933.1 | 7638.05 | 2192 | 22034.15 | -11271 | -933.1 | -7638.05 | -2192 | -22034.15 | 3600 | 1000 | 1050 | 0 | 5650 | OTH | WBS | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 3600 | OTH | WBS | 200 | 200 | 200 | 200 | 200 | [7 empty] | 1000 | OTH | WBS | 350 | 350 | 350 | [9 empty] | 1050 | OTH | WBS | [12 empty] | 0 | -14871 | -1933.1 | -8688.05 | -2192
44 | A03608X01P1 | WBS |  | Narrow Foot Roll-Spare | NA | AMAN SINGH | [7 empty] | 0 | 1047.3 |  | 1048.4 | 1740 | 3835.7 | -1047.3 | 0 | -1048.4 | -1740 | -3835.7 | 0 | 0 | 0 | 0 | 0 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | -1047.3 | 0 | -1048.4 | -1740
45 | 18010 | SO | 2 | OXYGEN LANCE | HOLD | AMULYA JENA | 2025-07-03 | 2026-02-28 | 5366 | 508 | 22 |  |  | 530 |  |  |  |  | 0 | 508 | 22 | 0 | 0 | 530 | 0 | 0 | 0 | 0 | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | 508 | 22 | 0 | 0
46 | 16925 | SO | 10 | ELBOW, BLOWPIPE & SIGHT HOLE COVER |  | SANGRAM SWAIN | 2025-07-17 | 2025-10-24 | 15000 | 800 | 60 |  | 140 | 1000 | 1624 | 178.6 | 297.3 | 447 | 2546.9 | -824 | -118.6 | -297.3 | -307 | -1546.9 | 0 | 0 | 0 | 0 | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | -824 | -118.6 | -297.3 | -307
47 | 18905 | SO | 2 | HYDRAULIC CYLINDER ASSEMBLY | NA only ass | Ravi Ranjan | 2025-07-25 | 2026-03-30 | 2889 | 8 | 164 |  | 80 | 252 | 7 | 91 | 426.7 |  | 524.7 | 1 | 73 | -426.7 | 80 | -272.7 | 0 | 0 | 0 | 0 | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | 1 | 73 | -426.7 | 80
48 | 21043 | SO | 1 | LADLE ROOF |  | Rejeesh | 2025-07-24 | 2026-09-25 | 10122 | 2642 |  | 140 | 200 | 2982 |  |  |  | 6 | 6 | 2642 | 0 | 140 | 194 | 2976 | 2642 | 0 | 140 | 194 | 2976 | OTH | DIRECT | 662 | 660 | 660 | 660 | [8 empty] | 2642 | OTH | DIRECT | [12 empty] | 0 | OTH | DIRECT |  |  | 140 | [9 empty] | 140 | OTH | DIRECT |  |  | 194 | [9 empty] | 194 | 0 | 0 | 0 | 0
49 | S000738EXP.ETP.EXR.CEH | 19815 | 1 | CONTAINER HOLDER |  | AMARSHI BEHERA | 2025-07-24 |  | 9731 | 1252 | 200 | 60 | 80 | 1592 | 1355 | 57 | 39 |  | 1451 | -103 | 143 | 21 | 80 | 141 | 0 | 143 | 21 | 80 | 244 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | 100 | 43 | [10 empty] | 143 | OTH | SERVICE | 21 | [11 empty] | 21 | OTH | SERVICE |  | 80 | [10 empty] | 80 | -103 | 0 | 0 | 0
50 | S000659CAS.SCP.STG.HOS S000659CAS.SCP.STG.HOS01 S000659CAS.SCP.STG.HOS02 | 17892 | 14 | SEGMENT 3-5 ROLLER ASSEMBLY |  | Kameshwaran | 2025-07-28 |  | 14374 | 36 |  | 320 | 280 | 636 | 220.06 | 817 | 340.04 |  | 1377.1 | -184.06 | -817 | -20.04 | 280 | -741.1 | 0 | 0 | 100 | 280 | 380 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | 100 | [11 empty] | 100 | OTH | SERVICE |  | 280 | [10 empty] | 280 | -184.06 | -817 | -120.04 | 0
51 | C01RB1PSMP.LSH.LTF.LTCK | WBS | 1 | EAF & LF TRANSFER CARS | NA | AVIJIT SAHA | 2025-07-02 |  | 25000 | 1985 | 148 | 32 | 300 | 2465 | 1748 | 173 | 304 | 333 | 2572 | 237 | -25 | -272 | -33 | -93 | 0 | 0 | 0 | 0 | 0 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | 237 | -25 | -272 | -33
52 | C01RB1PSMP.LHF.EAR.EASK | WBS | 1 | ELECTRODE ARM ASSEMBLY | NA | Ravi Ranjan | 2025-07-25 |  | 13557 | 4750 | 640 |  | 800 | 6190 | 5857 | 508 | 190 | 678 | 7233 | -1107 | 132 | -190 | 122 | -1043 | 0 | 0 | 0 | 30 | 30 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | OTH | WBS | 30 | [11 empty] | 30 | -1107 | 132 | -190 | 92
53 | C01RB1PSMP.LHF.ROS.WCRK | WBS | 1 | WATER COOLED ROOF | NA | REJEESH | 2025-07-25 |  | 8885 | 2253.25 | 46 |  |  | 2299.25 | 2573 | 1.4 | 34.1 | 22 | 2630.5 | -319.75 | 44.6 | -34.1 | -22 | -331.25 | 0 | 0 | 0 | 0 | 0 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | -319.75 | 44.6 | -34.1 | -22
54 | C01RB1PSMP.LSH.LTL.LTCK | WBS | 1 | Ladle transfer car (LF ladle car) | NA | AVIJIT SAHA |  |  | 25000 | 1975 | 148 | 32 | 300 | 2455 | 1770 | 148.6 | 361.55 | 117 | 2397.15 | 205 | -0.6 | -329.55 | 183 | 57.85 | 0 | 0 | 0 | 0 | 0 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | 205 | -0.6 | -329.55 | 183
55 | C01RB1PSMP.LSH.LTL.LTC2K | WBS | 1 | Ladle Transfer Car 2 Khurda | NA | AVIJIT SAHA |  |  | 25000 | 1985 | 148 | 32 | 300 | 2465 | 2364 | 114 | 154 | 312 | 2944 | -379 | 34 | -122 | -12 | -479 | 0 | 0 | 0 | 0 | 0 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | -379 | 34 | -122 | -12
56 | 19678 | SO | 1 | ROCKER FRAME ASSEMBLY |  | AMULYA JENA | 2025-08-01 | 2026-09-30 | 108785 | 13731 | 190 | 120 |  | 14041 | 9938 |  |  |  | 9938 | 3793 | 190 | 120 | 0 | 4103 | 3793 | 190 | 120 | 0 | 4103 | OTH | SERVICE | 1897 | 1896 | [10 empty] | 3793 | OTH | SERVICE |  | 90 | 100 | [9 empty] | 190 | OTH | SERVICE |  |  | 60 | 60 | [8 empty] | 120 | OTH | SERVICE | [12 empty] | 0 | 0 | 0 | 0 | 0
57 | A03607X01.10.3000 | WBS | 584 | MOULD FOOT ROLLER |  | AMAN SINGH | 2025-08-01 |  |  | 932 |  | 1165 | 60 | 2157 |  |  |  |  | 0 | 932 | 0 | 1165 | 60 | 2157 | 932 | 0 | 1165 | 60 | 2157 | OTH | WBS | 200 | 200 | 200 | 200 | 132 | [7 empty] | 932 | OTH | WBS | [12 empty] | 0 | OTH | WBS | 250 | 250 | 250 | 250 | 165 | [7 empty] | 1165 | OTH | WBS | 20 | 20 | 20 | [9 empty] | 60 | 0 | 0 | 0 | 0
58 | 18554 | SO | 1 | WATERBOX,NARROW FACE CARRIER INCLUDING NECKDOWN BOLT & SWIVEL JOINT |  | Kameshwaran | 2025-08-11 | 2026-04-20 | 9240 | 1710 | 188 | 55 |  | 1953 | 767 | 179 | 50 |  | 996 | 943 | 9 | 5 | 0 | 957 | 943 | 150 | 5 | 60 | 1158 | OTH | SERVICE | 472 | 471 | [10 empty] | 943 | OTH | SERVICE |  |  | 150 | [9 empty] | 150 | OTH | SERVICE | 5 | [11 empty] | 5 | OTH | SERVICE |  |  |  | 60 | [8 empty] | 60 | 0 | -141 | 0 | -60
59 | 19070 | SO | 4 | TOP & BOTTOM CHOCKS | NA only ass | SHASHIKUMAR | 2025-08-19 |  |  | 178 | 320 |  | 650 | 1148 |  |  |  |  | 0 | 178 | 320 | 0 | 650 | 1148 | 0 | 320 | 650 | 0 | 970 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | 320 | [11 empty] | 320 | OTH | SERVICE | 650 | [11 empty] | 650 | OTH | SERVICE | [12 empty] | 0 | 178 | 0 | -650 | 650
60 | 18082 | SO | 5 | DOWNLEG ARRANGEMENT |  | SANGRAM SWAIN | 2025-08-20 | 2026-02-18 | 1453 | 328 |  |  | 80 | 408 | 574 |  | 22 | 125 | 721 | -246 | 0 | -22 | -45 | -313 | 0 | 0 | 0 | 0 | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | -246 | 0 | -22 | -45
61 | 20565 | SO | 1 | ETA PRESS 66- BALER ASSEMBLY |  | KRISHNASIS | 2025-08-11 | 2026-05-31 | 158000 | 12420 | 670 | 1080 | 2500 | 16670 | 13633 | 875 | 192 | 461 | 15161 | -1213 | -205 | 888 | 2039 | 1509 | 300 | 600 | 888 | 2039 | 3827 | Contract | DIRECT | 300 | [11 empty] | 300 | Contract | DIRECT | 600 | [11 empty] | 600 | Contract | DIRECT | 445 | 443 | [10 empty] | 888 | Contract | DIRECT | 1020 | 1019 | [10 empty] | 2039 | -1513 | -805 | 0 | 0
62 | 21311 | SO | 1 | HSM F2 MAIN GB HOUSING |  | ARUN KUMAR | 2025-09-09 | 2026-06-30 | 13580 | 1182 | 170 | 120 | 80 | 1552 | 1055 | 53.2 | 16.9 |  | 1125.1 | 127 | 116.8 | 103.1 | 80 | 426.9 | 127 | 116.5 | 103 | 80 | 426.5 | OTH | SERVICE | 127 | [11 empty] | 127 | OTH | SERVICE | 35 | 81.5 | [10 empty] | 116.5 | OTH | SERVICE | 103 | [11 empty] | 103 | OTH | SERVICE |  | 80 | [10 empty] | 80 | 0 | 0.3 | 0.1 | 0
63 | 21615 | SO | 1 | RECONDITIONING OF WR & BUR CHOCKS |  | RAVI RANJAN/SAMBIT | 2025-09-12 | 2026-05-26 | 76705 |  |  |  | 100 | 100 | 1 | 116.5 | 1786 | 1169 | 3072.5 | -1 | -116.5 | -1786 | -1069 | -2972.5 | 0 | 0 | 0 | 0 | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | -1 | -116.5 | -1786 | -1069
64 | A02261M210.30.10.11P1010 | WBS | 2 | LOWER SHELL |  | AMULYA JENA | 2025-09-15 | 31ST MAR'26 15TH MAY'26 | 109414 | 9200 |  | 200 |  | 9400 | 6333.31 | 308 | 138 |  | 6779.31 | 2866.69 | -308 | 62 | 0 | 2620.69 | 2867 | 0 | 62 | 0 | 2929 | OTH | WBS | 1433.5 | 1433.5 | [10 empty] | 2867 | OTH | WBS | [12 empty] | 0 | OTH | WBS | 62 | [11 empty] | 62 | OTH | WBS | [12 empty] | 0 | -0.31 | -308 | 0 | 0
65 | A02261M210.30.10.11P1020 | WBS | 2 | UPPER SHELL | NA | REJEESH | 2025-09-15 | 31ST MAR'26 15TH MAY'26 | 63966 | 11470 |  | 200 |  | 11670 | 12229.14 | 11.8 | 517.12 |  | 12758.06 | -759.14 | -11.8 | -317.12 | 0 | -1088.06 | 4437 | 3 | 165 | 0 | 4605 | OTH | WBS | 4437 | [11 empty] | 4437 | OTH | WBS | 3 | [11 empty] | 3 | OTH | WBS | 165 | [11 empty] | 165 | OTH | WBS | [12 empty] | 0 | -5196.14 | -14.8 | -482.12 | 0
66 | A02261M210.30.10.11P1010 | WBS | 12 | INJECTOR BOX - 2 PC ,OXYGEN INJECTOR -10 PC |  | RAVI RANJAN | 2025-09-25 | 31ST MAR'26 15TH MAY'26 | 1780 | 776 | 62 | 240 |  | 1078 |  |  |  |  | 0 | 776 | 62 | 240 | 0 | 1078 | 776 | 62 | 240 | 0 | 1078 | OTH | WBS | 776 | [11 empty] | 776 | OTH | WBS |  | 62 | [10 empty] | 62 | OTH | WBS | 240 | [11 empty] | 240 | OTH | WBS | [12 empty] | 0 | 0 | 0 | 0 | 0
67 | 22002 | SO | 1 | CVC BLOCK F5-F7 OP EXIT SIDE |  | RAVI RANJAN/SASHI | 2025-09-19 | 2026-02-17 | 1781 |  | 230 |  | 100 | 330 | 15 | 234.5 | 164.5 |  | 414 | -15 | -4.5 | -164.5 | 100 | -84 | 0 | 0 | 0 | 100 | 100 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | 100 | [11 empty] | 100 | -15 | -4.5 | -164.5 | 0
68 | S000722CAS.SCP.STG.HOS | 21135 | 1 | SEGMENT 7(Loose side) |  | Kameshwaran | 2025-09-19 | 2026-06-30 | 33920 | 310 | 190 | 190 | 300 | 990 | 1068.3 | 23.8 | 72.6 |  | 1164.7 | -758.3 | 166.2 | 117.4 | 300 | -174.7 | 100 | 166 | 0 | 300 | 566 | OTH | SERVICE | 100 | [11 empty] | 100 | OTH | SERVICE | 166 | [11 empty] | 166 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE |  | 300 | [10 empty] | 300 | -858.3 | 0.2 | 117.4 | 0
69 | 14154 | SO | 1 | PIVOT ARM | NA | SHASHIKUMAR | 2025-09-22 | 2026-02-17 | 5816 | 7 | 113 |  |  | 120 | 10.8 | 183 | 39.45 | 10 | 243.25 | -3.8 | -70 | -39.45 | -10 | -123.25 | 0 | 0 | 0 | 0 | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | -3.8 | -70 | -39.45 | -10
70 | 22085 | SO | 3 | EAF ROOF SPOKE FRAME,ROOF LIFTING FRAME & LIFTING FORK |  | REJEESH | 2025-09-23 | 2026-04-30 | 27289 | 3800 | 40 | 28 |  | 3868 | 3634.5 | 14.6 | 47.65 |  | 3696.75 | 165.5 | 25.4 | -19.65 | 0 | 171.25 | 166 | 25 | 0 | 0 | 191 | OTH | SERVICE | 166 | [11 empty] | 166 | OTH | SERVICE | 25 | [11 empty] | 25 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | -0.5 | 0.4 | -19.65 | 0
71 | 21010 | SO | 1 | REFURBISHMENT OF LSV/USV DRIVE |  | SANGRAM SWAIN | 2025-09-30 |  | 210 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | 0 | 0 | 0 | 0
72 | S000850SMP.FTP.WCG.DUC S000850SMP.FTP.WCG.COH | 24910 | 3 | COOLED DUCT, MOVABLE ELBOW & MOVABLE ELBOW |  | REJEESH | 2025-10-01 | 2026-11-30 | 163400 | 67096 | 1634 |  |  | 68730 | 5641.06 |  |  |  | 5641.06 | 61454.94 | 1634 | 0 | 0 | 63088.94 | 61455 | 1633 | 0 | 0 | 63088 | Group | DIRECT | 10242.5 | 10242.5 | 10242.5 | 10242.5 | 10242.5 | 10242.5 | [6 empty] | 61455 | Group | DIRECT | 327 | 327 | 327 | 326 | 326 | [7 empty] | 1633 | Group | DIRECT | [12 empty] | 0 | Group | DIRECT | [12 empty] | 0 | -0.06 | 1 | 0 | 0
73 | 22574 | SO | 2 | EAF UPPER SHELL FRAME W/SLAG DOOR & EAF ROOF SPOKE FRAME |  | REJEESH | 2025-10-01 | 2026-06-20 | 13252 | 4670 |  | 46 |  | 4716 | 323 |  |  |  | 323 | 4347 | 0 | 46 | 0 | 4393 | 4347 | 0 | 46 | 0 | 4393 | OTH | SERVICE | 1449 | 1449 | 1449 | [9 empty] | 4347 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE |  |  | 46 | [9 empty] | 46 | OTH | SERVICE | [12 empty] | 0 | 0 | 0 | 0 | 0
74 | 22797 | SO | 5 | SKIRT ASSEMBLY, LOWER STACK, COOLING RING, MOVABLE SKIRT & LOWER HOOD |  | REJEESH | 2025-10-08 | 2026-05-31 | 46190 | 10456 |  | 240 |  | 10696 | 5411 |  |  |  | 5411 | 5045 | 0 | 240 | 0 | 5285 | 5045 | 0 | 240 | 0 | 5285 | OTH | SERVICE | 1261.25 | 1261.25 | 1261.25 | 1261.25 | [8 empty] | 5045 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | 40 | 100 | 100 | [9 empty] | 240 | OTH | SERVICE | [12 empty] | 0 | 0 | 0 | 0 | 0
75 | 23426 | SO | 1 | DIPPER HANDLE ASSY |  | AVIJIT SAHA | 2025-10-01 | 2026-07-20 | 47405 |  |  |  | 50 | 50 |  |  |  |  | 0 | 0 | 0 | 0 | 50 | 50 | 0 | 0 | 0 | 50 | 50 | Contract | DIRECT | [12 empty] | 0 | Contract | DIRECT | [12 empty] | 0 | Contract | DIRECT | [12 empty] | 0 | Contract | DIRECT |  | 50 | [10 empty] | 50 | 0 | 0 | 0 | 0
76 | 23424 | SO | 1 | HANDLE MACHINING |  | AVIJIT SAHA | 2025-10-01 | 2026-07-15 | 47405 | 4112.2759 | 110 | 255 |  | 4477.2759 | 3940 |  |  |  | 3940 | 172.2759 | 110 | 255 | 0 | 537.2759 | 172 | 110 | 255 | 0 | 537 | Contract | DIRECT | 100 | 72 | [10 empty] | 172 | Contract | DIRECT |  | 110 | [10 empty] | 110 | Contract | DIRECT |  | 255 | [10 empty] | 255 | Contract | DIRECT | [12 empty] | 0 | 0.27592 | 0 | 0 | 0
77 | 22795 | SO | 2 | ASSEMBLY ABGT L4000 & ACC. |  | SANGRAM SWAIN | 2025-10-10 | 2026-02-21 | 6100 | 1850 |  | 40 |  | 1890 | 115.45 |  | 22.8 |  | 138.25 | 1734.55 | 0 | 17.2 | 0 | 1751.75 | 1735 | 0 | 17 | 0 | 1752 | OTH | SERVICE | 579 | 578 | 578 | [9 empty] | 1735 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE |  | 17 | [10 empty] | 17 | OTH | SERVICE | [12 empty] | 0 | -0.45 | 0 | 0.2 | 0
78 | S000781CAS1.SCP.STG.HOS S000781CAS2.SCP.STG.HOS S000781CAS3.SCP.STG.HOS | 22335 | 24 | ROLLER ASSEMBLY | NA only ass | Kameshwaran | 2025-10-16 | 2026-06-30 | 13570 | 22 |  |  | 400 | 422 |  |  |  |  | 0 | 22 | 0 | 0 | 400 | 422 | 0 | 0 | 0 | 400 | 400 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE |  |  | 400 | [9 empty] | 400 | 22 | 0 | 0 | 0
79 | 23583 | SO | 3 | REFURBISHMENT OF DISTRIBUTION CHUTE -3.8 & 3.5 |  | SANGRAM SWAIN | 2025-10-22 | 2026-07-17 | 9710 |  |  | 18 | 500 | 518 | 15.5 | 35.4 | 6 | 25.5 | 82.4 | -15.5 | -35.4 | 12 | 474.5 | 435.6 | 0 | 0 | 12 | 0 | 12 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | 12 | [11 empty] | 12 | OTH | SERVICE | [12 empty] | 0 | -15.5 | -35.4 | 0 | 474.5
80 | 23047 | SO | 1 | ROLL FORCE CYLINDER VERTICAL AGC |  | SHASHIKUMAR | 2025-10-22 | 2026-05-22 | 3413 | 24 | 852 | 152 | 192 | 1220 |  |  | 215 |  | 215 | 24 | 852 | -63 | 192 | 1005 | 24 | 852 | 0 | 0 | 876 | OTH | SERVICE | 24 | [11 empty] | 24 | OTH | SERVICE | 426 | 426 | [10 empty] | 852 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | 0 | 0 | -63 | 192
81 | 23634 | SO | 5 | ADJUSTING SKIRT & INSPECTION COVER | APEX | REJEESH | 2025-10-27 | 2026-07-28 | 19350 | 4969.5 | 110 |  |  | 5079.5 |  |  |  |  | 0 | 4969.5 | 110 | 0 | 0 | 5079.5 | 0 | 0 | 0 | 0 | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | 4969.5 | 110 | 0 | 0
82 | 23814 | SO | 1 | SPARE;COOLING RING FOR VESSEL 3,VESSEL |  | REJEESH | 2025-10-28 | 2026-06-23 | 6587 | 1514 |  | 46 |  | 1560 | 893.8 |  |  |  | 893.8 | 620.2 | 0 | 46 | 0 | 666.2 | 620 | 0 | 46 | 0 | 666 | OTH | SERVICE | 310 | 310 | [10 empty] | 620 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE |  | 46 | [10 empty] | 46 | OTH | SERVICE | [12 empty] | 0 | 0.2 | 0 | 0 | 0
83 | 24007 | SO | 2 | BOOM & ARM |  | Kameshwaran | 2025-10-25 | 2026-07-10 | 44190 | 3125 | 175 | 87 | 150 | 3537 | 865 |  |  |  | 865 | 2260 | 175 | 87 | 150 | 2672 | 2260 | 175 | 87 | 50 | 2572 | Contract | DIRECT | 754 | 753 | 753 | [9 empty] | 2260 | Contract | DIRECT | 75 |  |  | 100 | [8 empty] | 175 | Contract | DIRECT | 87 | [11 empty] | 87 | Contract | DIRECT |  |  |  | 50 | [8 empty] | 50 | 0 | 0 | 0 | 100
84 | 23817 | SO | 1 | SPARE KIT FOR GSSV ND1200 | NA | SANGRAM SWAIN | 2025-10-30 | 2025-12-16 | 2800 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | 0 | 0 | 0 | 0
85 | 18848 | SO | 1 | REFURBISHMENT OF DISTRIBUTION CHUTE -REINFORCED TYPE |  | SANGRAM SWAIN | 2025-10-30 |  | 6820 |  | 40 |  | 500 | 540 |  |  |  | 112 | 112 | 0 | 40 | 0 | 388 | 428 | 0 | 40 | 0 | 0 | 40 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE |  |  |  | 40 | [8 empty] | 40 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | 0 | 0 | 0 | 388
86 | 22911 | SO | 2 | COOLING RING & SKIRT WITH LIFTING BRACKET |  | REJEESH | 2025-10-09 | 2026-08-08 | 6650 | 1676 |  | 46 |  | 1722 | 191 |  |  |  | 191 | 1485 | 0 | 46 | 0 | 1531 | 1485 | 0 | 46 | 0 | 1531 | OTH | SERVICE | 297 | 297 | 297 | 297 | 297 | [7 empty] | 1485 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE |  |  |  | 46 | [8 empty] | 46 | OTH | SERVICE | [12 empty] | 0 | 0 | 0 | 0 | 0
87 | A03520M220.35.20.60P1100 | WBS | 1 | INTERBAY TRANSFER CAR |  | ARUN KUMAR | 2025-11-04 | 2026-09-10 | 88945 | 6755 | 130 | 42.7 | 700 | 7627.7 | 5122 | 205 | 43 |  | 5370 | 1633 | -75 | -0.3 | 700 | 2257.7 | 1633 | 120 | 30 | 580 | 2363 | OTH | WBS | 1000 | 633 | [10 empty] | 1633 | OTH | WBS | 60 | 60 | [10 empty] | 120 | OTH | WBS | 22 | 8 | [10 empty] | 30 | OTH | WBS |  |  |  | 580 | [8 empty] | 580 | 0 | -195 | -30.3 | 120
88 | 23985 | SO | 2 | DEWATERING DRUM & FEEDING OF DRUM |  | SANGRAM SWAIN | 2025-11-04 | 2026-08-30 | 42450 | 1125 | 16 | 40 |  | 1181 | 4797 | 199.8 | 81.15 |  | 5077.95 | -3672 | -183.8 | -41.15 | 0 | -3896.95 | 0 | 0 | 0 | 0 | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | -3672 | -183.8 | -41.15 | 0
89 | S000645SMP.HMH.HMC.LTCKH | 18685 | 3 | HOT METAL TRANSFER CAR FOR KR-2 + 2 YEARS SPARE |  | ARUN KUMAR | 2025-11-04 | 2026-09-10 | 169540 | 6755 | 130 | 170 | 700 | 7755 | 2609 |  |  |  | 2609 | 4146 | 130 | 170 | 700 | 5146 | 4146 | 70 | 70 | 600 | 4886 | OTH | SERVICE | 1037 | 1037 | 1036 | 1036 | [8 empty] | 4146 | OTH | SERVICE |  |  |  |  | 70 | [7 empty] | 70 | OTH | SERVICE |  |  |  |  | 70 | [7 empty] | 70 | OTH | SERVICE | [5 empty] | 300 | 300 | [5 empty] | 600 | 0 | 60 | 100 | 100
90 | 24358 | SO | 1 | MANDREL BEARING HOUSING |  | ARUN KUMAR | 2025-11-07 | 2026-07-30 | 8472 | 1182 | 170 | 120 | 80 | 1552 | 823.78 |  |  |  | 823.78 | 358.22 | 170 | 120 | 80 | 728.22 | 358 | 170 | 120 | 80 | 728 | OTH | SERVICE |  | 179 | 179 | [9 empty] | 358 | OTH | SERVICE |  |  |  | 170 | [8 empty] | 170 | OTH | SERVICE |  |  | 120 | [9 empty] | 120 | OTH | SERVICE |  |  |  | 80 | [8 empty] | 80 | 0.22 | 0 | 0 | 0
91 | 24341 | SO | 2 | REFURBISHMENT OF DISTRIBUTION CHUTE L-4M REFURBISHMENT OF HOT BLAST VALVE ND 1600 | dispatched-10 | SANGRAM SWAIN | 2025-10-22 | 2027-07-14 | 29870 | 216 | 12 |  | 12 | 240 | 13.3 | 19.3 | 17.5 | 492.5 | 542.6 | 202.7 | -7.3 | -17.5 | -480.5 | -302.6 | 203 | 0 | 0 | 0 | 203 | OTH | SERVICE | 203 | [11 empty] | 203 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | -0.3 | -7.3 | -17.5 | -480.5
92 | 24277 | SO | 2 | REFURBISHMENT OF LMG DRIVE REFURBISHMENT OF DISTRIBUTION CHUTE L-4M | DONE | SANGRAM SWAIN | 2025-11-10 | 2025-11-10 | 3430 |  |  | 500 | 400 | 900 |  |  |  | 50 | 50 | 0 | 0 | 500 | 350 | 850 | 0 | 0 | 500 | 0 | 500 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE |  |  |  | 250 | 250 | [7 empty] | 500 | OTH | SERVICE | [12 empty] | 0 | 0 | 0 | 0 | 350
93 | S000885CAS.SCP.STG.HOS | 26179 | 1 | SEGMENT 8 |  | Kameshwaran | 2025-11-11 | 2026-11-30 | 39000 | 2605 | 280 | 160 | 800 | 3845 | 7 |  |  |  | 7 | 2598 | 280 | 160 | 800 | 3838 | 2598 | 280 | 160 | 800 | 3838 | OTH | SERVICE |  | 862 | 868 | 868 | [8 empty] | 2598 | OTH | SERVICE |  |  |  | 140 | 140 | [7 empty] | 280 | OTH | SERVICE |  |  |  | 60 | 100 | [7 empty] | 160 | OTH | SERVICE | [5 empty] | 400 | 400 | [5 empty] | 800 | 0 | 0 | 0 | 0
94 | 22661 | SO | 2 | DISTRIBUTION ROCKER NONE DRIVE ASSEMBLY DISTRIBUTOR ROCKER DRIVE CYLINDER SIDE | NA | SANGRAM SWAIN | 2025-11-12 | 2026-03-22 | 1214 |  |  |  |  | 0 |  |  |  | 60 | 60 | 0 | 0 | 0 | -60 | -60 | 0 | 0 | 0 | 0 | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | 0 | 0 | 0 | -60
95 | 24971 | SO | 2 | SPARE KIT FOR LSV DRIVE ND900 DISTRIBUTOR ROCKER DRIVE CYLINDER SIDE | NA | SANGRAM SWAIN | 2025-11-21 | 2026-10-07 | 6490 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | 0 | 0 | 0 | 0
96 | 23007 | SO | 2 | FINAL MACHINNG OF TOP EDGER CHOCK FINAL MACHINNG OF BOTTOM EDGER CHOCK | NA | ARUN KUMAR | 2025-11-17 |  | 18230 |  | 390 |  |  | 390 |  |  |  |  | 0 | 0 | 390 | 0 | 0 | 390 | 0 | 0 | 0 | 0 | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | 0 | 390 | 0 | 0
97 | 23097 | SO | 1 | ROTATING FRAME ASSY OF GRIP TYPE TILTER |  | RAVI RANJAN/AMAN | 2025-11-20 | 2026-06-06 | 9362 | 833 | 98 | 32 | 200 | 1163 | 264.24 |  |  |  | 264.24 | 568.76 | 98 | 32 | 200 | 898.76 | 569 | 90 | 32 | 160 | 851 | OTH | SERVICE | 169 | 200 | 200 | [9 empty] | 569 | OTH | SERVICE | 45 | 45 | [10 empty] | 90 | OTH | SERVICE | 32 | [11 empty] | 32 | OTH | SERVICE |  |  |  | 160 | [8 empty] | 160 | -0.24 | 8 | 0 | 40
98 | S000847CSP.TSC.STG.SSF S000847CSP.TSC.CAB.RUS | 25240 | 2 | CARRIER FRAME & SEGMENT REMOVAL RAILS | NA | AMULYA JENA | 2025-11-26 | 2026-01-16 | 42310 | 2633.3168 | 720 |  | 350 | 3703.3168 | 4629.6 | 79.2 |  |  | 4708.8 | -1996.2832 | 640.8 | 0 | 350 | -1005.4832 | 0 | 0 | 0 | 0 | 0 | Group | DIRECT | [12 empty] | 0 | Group | DIRECT | [12 empty] | 0 | Group | DIRECT | [12 empty] | 0 | Group | DIRECT | [12 empty] | 0 | -1996.2832 | 640.8 | 0 | 350
99 | 25264 | SO | 2 | SPARE- VESSEL GUIDE | NA | KRISHNASIS | 2025-11-27 | 2026-03-15 | 1690 | 216 | 84 |  |  | 300 | 45.29 | 102.9 | 43.5 |  | 191.69 | 170.71 | -18.9 | -43.5 | 0 | 108.31 | 0 | 0 | 0 | 0 | 0 | Group | DIRECT | [12 empty] | 0 | Group | DIRECT | [12 empty] | 0 | Group | DIRECT | [12 empty] | 0 | Group | DIRECT | [12 empty] | 0 | 170.71 | -18.9 | -43.5 | 0
100 | S000823CFP.MCP.CDF.ECS | 23960 | 3 | FINAL MACHINING OF LAY SHAFT FOR 4000 TON PAD CARRIER -BREAK HUB CLUTCH HUB |  | RAVI RANJAN | 2025-11-28 |  | 8438 |  | 252 | 90 |  | 342 | 150 |  |  |  | 150 | -150 | 252 | 90 | 0 | 192 | 25 | 252 | 90 | 0 | 367 | OTH | SERVICE | 25 | [11 empty] | 25 | OTH | SERVICE | 126 | 126 | [10 empty] | 252 | OTH | SERVICE | 20 | 70 | [10 empty] | 90 | OTH | SERVICE | [12 empty] | 0 | -175 | 0 | 0 | 0
101 | 26954 | SO |  | OIL GUM,SPLIT BEARING BUSH,COVER,SPLIT RING, DOWEL PINS | NA | Sambit Sahoo | 2025-12-05 | 2026-06-05 | [5 empty] | 0 | 49.6 |  |  |  | 49.6 | -49.6 | 0 | 0 | 0 | -49.6 | 0 | 0 | 0 | 0 | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | -49.6 | 0 | 0 | 0
102 | 25457 | SO | 4 | BUR CHOCK -TOP & BOTTOM -OS & DS |  | SHASHIKUMAR | 2025-12-08 | 2026-11-25 | 24613 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | 0 | 0 | 0 | 0
103 | 25686 | SO | 2 | SUPP. WHEEL D710/240 WITHOUT GUID. & ACC SUPP. WHEEL D710/240 WITH GUID. & ACC | NA | SANGRAM SWAIN | 2025-12-10 | 2026-06-30 | 3820 | 5 | 4 | 6 | 30 | 45 |  |  |  |  | 0 | 5 | 4 | 6 | 30 | 45 | 0 | 0 | 0 | 0 | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | 5 | 4 | 6 | 30
104 | 24765 | SO | 1 | NEW REINFORCED DISTRIBUTION CHUTE L-4.5M |  | SANGRAM SWAIN | 2025-12-10 | 2026-05-13 | 6820 | 84 | 64 |  | 288 | 436 | 28 | 49.2 | 61 | 16 | 154.2 | 56 | 14.8 | -61 | 272 | 281.8 | 56 | 15 | 0 | 272 | 343 | OTH | SERVICE | 56 | [11 empty] | 56 | OTH | SERVICE | 15 | [11 empty] | 15 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | 100 | 172 | [10 empty] | 272 | 0 | -0.2 | -61 | 0
105 | 25952 | SO | 2 | REFURBISHMENT OF COLD BLAST VALVE |  | SANGRAM SWAIN | 2025-12-11 | 2026-02-28 | 3960 |  | 20 |  | 39 | 59 |  |  |  | 65 | 65 | 0 | 20 | 0 | -26 | -6 | 0 | 20 | 0 | 0 | 20 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | 20 | [11 empty] | 20 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | 0 | 0 | 0 | -26
106 | 26201 | SO | 4 | REFURBISHMENT OF INBA SUPPORT ROLLER |  | SANGRAM SWAIN | 2025-12-18 | 2026-12-07 | [5 empty] | 0 |  |  |  | 7 | 7 | 0 | 0 | 0 | -7 | -7 | 0 | 0 | 0 | 0 | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | 0 | 0 | 0 | -7
107 | S000851BFP.BLF.BLP.STC | 25368 | 1 | STAVE REPLACEMENT AT TSM | NA | SANGRAM SWAIN | 2025-12-22 | 2026-12-07 | [5 empty] | 0 |  |  |  | 185 | 185 | 0 | 0 | 0 | -185 | -185 | 0 | 0 | 0 | 0 | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | 0 | 0 | 0 | -185
108 | S000924SMP.EAF.FSH1 S000924SMP.EAF.FSH2 | 26562 | 2 | FURNACE SHELL |  | AMULYA JENA | 2025-12-29 | 2026-09-15 | 159690 | 13150 | 260 |  |  | 13410 | 6763 |  |  |  | 6763 | 6387 | 260 | 0 | 0 | 6647 | 6387 | 260 | 0 | 0 | 6647 | Group | DIRECT | 1065 | 1065 | 1065 | 1064 | 1064 | 1064 | [6 empty] | 6387 | Group | DIRECT |  |  | 100 | 160 | [8 empty] | 260 | Group | DIRECT | [12 empty] | 0 | Group | DIRECT | [12 empty] | 0 | 0 | 0 | 0 | 0
109 | S000771CSP.TSC.STG.BED | 21143 | 1 | SUPPORT ROLLER ASSEMBLY-CLADDING+MACHINING +ASSEMBLY |  | AMAN SINGH | 2025-12-29 | 2026-05-30 | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 10 | 32 | 24 | 106 | OTH | SERVICE |  | 40 | [10 empty] | 40 | OTH | SERVICE |  | 10 | [10 empty] | 10 | OTH | SERVICE |  | 32 | [10 empty] | 32 | OTH | SERVICE |  | 24 | [10 empty] | 24 | -40 | -10 | -32 | -24
110 | S000874CSP.RCA.ERA.ROT | 24096 | 1 | TRANSPORT ROLLER ASSEMBLY-ASSEMBLY |  | AMAN SINGH | 2025-12-24 | 2026-07-28 | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 10 | 32 | 24 | 106 | OTH | SERVICE |  | 40 | [10 empty] | 40 | OTH | SERVICE |  | 10 | [10 empty] | 10 | OTH | SERVICE |  | 32 | [10 empty] | 32 | OTH | SERVICE |  | 24 | [10 empty] | 24 | -40 | -10 | -32 | -24
111 | 26585 | SO | 1 | REFURBISHMENT OF GRITZKO VALVE | NA | SANGRAM SWAIN | 2026-01-02 | [6 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | 0 | 0 | 0 | 0
112 | 26584 | SO | 1 | DRUM DEFLECTOR PLATE | DONE | SANGRAM SWAIN | 2026-01-06 | 2026-07-27 | 3067 | 6 |  |  | 12 | 18 |  |  |  |  | 0 | 6 | 0 | 0 | 12 | 18 | 0 | 0 | 0 | 0 | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | 6 | 0 | 0 | 12
113 | 25638 | SO | 6 | DISTRIBUTION ROCKER CHUTE OCTAGONAL CHUTE WEAR LINER FOR SEAT ACC | DONE | SANGRAM SWAIN | 2026-01-06 | 2026-08-12 | 5770 | 100 |  |  |  | 100 | 74.9 |  | 2 |  | 76.9 | 25.1 | 0 | -2 | 0 | 23.1 | 25 | 0 | 0 | 0 | 25 | OTH | SERVICE |  |  | 25 | [9 empty] | 25 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | 0.1 | 0 | -2 | 0
114 | 26093 | SO | 1 | REFURBISHMENT OF DISTRIBUTION CHUTE L-5M | NA | SANGRAM SWAIN | 2026-01-12 | 2026-03-01 | 8057 |  |  |  |  | 0 | 11.05 | 32 |  | 277 | 320.05 | -11.05 | -32 | 0 | -277 | -320.05 | 0 | 0 | 0 | 0 | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | -11.05 | -32 | 0 | -277
115 | 27471 | SO | 6 | BEARING LEVER, KING PIN, UPRIGHT-LEFT, UPRIGHT-RIGHT |  | Amulya Jena | 2026-01-14 | 2026-08-15 | 2940 | 1212 | 75 | 210 |  | 1497 | 1170 |  | 53.4 |  | 1223.4 | 42 | 75 | 156.6 | 0 | 273.6 | 42 | 75 | 157 | 0 | 274 | Contract | DIRECT |  | 42 | [10 empty] | 42 | Contract | DIRECT | [5 empty] | 75 | [6 empty] | 75 | Contract | DIRECT |  |  | 57 | 50 | 50 | [7 empty] | 157 | Contract | DIRECT | [12 empty] | 0 | 0 | 0 | -0.4 | 0
116 | 27391 | SO | 1 | SIDEBAR REFURBISHMENT |  | RAVI RANJAN/SASHI | 2026-01-15 | 2026-05-29 |  | 400 | 200 |  |  | 600 | 43 |  |  |  | 43 | 357 | 200 | 0 | 0 | 557 | 357 | 200 | 0 | 0 | 557 | Contract | DIRECT | 150 | 207 | [10 empty] | 357 | Contract | DIRECT |  | 200 | [10 empty] | 200 | Contract | DIRECT | [12 empty] | 0 | Contract | DIRECT | [12 empty] | 0 | 0 | 0 | 0 | 0
117 | 26564 | SO | 1 | DISTRIBUTION CHUTE L-4M |  | SANGRAM SWAIN | 2026-01-12 | 2026-12-27 | 6086 | 84 | 64 |  | 240 | 388 |  |  |  |  | 0 | 84 | 64 | 0 | 240 | 388 | 84 | 64 | 0 | 100 | 248 | OTH | SERVICE |  | 84 | [10 empty] | 84 | OTH | SERVICE |  | 64 | [10 empty] | 64 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [5 empty] | 100 | [6 empty] | 100 | 0 | 0 | 0 | 140
118 | 27361 | SO | 42 | REFURBISHMENT OF DOWNLEGS | NA only ass | SANGRAM SWAIN | 2026-01-20 | 2026-05-31 | 91000 |  |  |  | 840 | 840 |  |  |  | 30 | 30 | 0 | 0 | 0 | 810 | 810 | 0 | 0 | 0 | 0 | 0 | Contract | SERVICE | [12 empty] | 0 | Contract | SERVICE | [12 empty] | 0 | Contract | SERVICE | [12 empty] | 0 | Contract | SERVICE | [12 empty] | 0 | 0 | 0 | 0 | 810
119 | 26581 | SO | 1 | REFURBISHMENT OF HOT BLAST VALVE |  | SANGRAM SWAIN | 2026-01-22 |  | 25000 |  |  |  |  | 0 |  |  | 23 | 104 | 127 | 0 | 0 | -23 | -104 | -127 | 0 | 0 | 0 | 0 | 0 | Contract | SERVICE | [12 empty] | 0 | Contract | SERVICE | [12 empty] | 0 | Contract | SERVICE | [12 empty] | 0 | Contract | SERVICE | [12 empty] | 0 | 0 | 0 | -23 | -104
120 | 27917 | SO | 1 | DEWATERING DRUM-D5000x6250 |  | SANGRAM SWAIN | 2026-01-28 | 2027-01-08 | 47973 | 7648 | 270 | 110 |  | 8028 | 5356 |  |  | 13.7 | 5369.7 | 2292 | 270 | 110 | -13.7 | 2658.3 | 2292 | 270 | 110 | 0 | 2672 | OTH | SERVICE | 764 | 764 | 382 | 382 | [8 empty] | 2292 | OTH | SERVICE |  |  | 100 | 170 | [8 empty] | 270 | OTH | SERVICE |  |  | 110 | [9 empty] | 110 | OTH | SERVICE | [12 empty] | 0 | 0 | 0 | 0 | -13.7
121 | 28231 | SO | 2 | FRAMING PARTS (CLADDED) FRAMING PARTS (SS 304L) |  | AMULYA JENA | 2026-01-19 | 2026-08-30 | 28500 | 4275 | 600 |  |  | 4875 |  |  |  |  | 0 | 4275 | 600 | 0 | 0 | 4875 | 4275 | 600 | 0 | 0 | 4875 | Contract | DIRECT |  | 1069 | 1069 | 1069 | 1068 | [7 empty] | 4275 | Contract | DIRECT |  | 300 | 300 | [9 empty] | 600 | Contract | DIRECT | [12 empty] | 0 | Contract | DIRECT | [12 empty] | 0 | 0 | 0 | 0 | 0
122 | 28288 | SO | 3 | BALE SLIDE, FLAP ASSEMBLY & OIL PAN ASSEMBLY |  | KRISHNASIS | 2026-01-28 | 2026-05-31 |  | 975 | 12 |  |  | 987 |  |  |  |  | 0 | 975 | 12 | 0 | 0 | 987 | 975 | 12 | 0 | 0 | 987 | Contract | DIRECT | 975 | [11 empty] | 975 | Contract | DIRECT | 12 | [11 empty] | 12 | Contract | DIRECT | [12 empty] | 0 | Contract | DIRECT | [12 empty] | 0 | 0 | 0 | 0 | 0
123 | 24094 | SO | 1 | EBT TOP SHELL |  | Rejeesh | 2026-01-14 | 2026-08-30 | 5075 | 968 |  | 14 |  | 982 | 13 |  |  |  | 13 | 955 | 0 | 14 | 0 | 969 | 955 | 0 | 14 | 0 | 969 | OTH | SERVICE | 955 | [11 empty] | 955 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | 14 | [11 empty] | 14 | OTH | SERVICE | [12 empty] | 0 | 0 | 0 | 0 | 0
124 | S000993SMP.EAF.GYS.GNY | 28641 | 3 | Swing bridge, Frame & Electrode regulating cylinder |  | AVIJIT SAHA | 2026-02-11 | 30-10-2026 31-12-2026 | 213215.5 | 24966 | 306 | 292 | 450 | 26014 | 951.93 |  |  |  | 951.93 | 24014.07 | 306 | 292 | 450 | 25062.07 | 24014 | 306 | 292 | 450 | 25062 | Group | DIRECT | 3431 | 3431 | 3431 | 3431 | 3430 | 3430 | 3430 | [5 empty] | 24014 | Group | DIRECT |  |  | 125 | 125 |  |  | 56 | [5 empty] | 306 | Group | DIRECT |  |  | 100 | 100 | 92 | [7 empty] | 292 | Group | DIRECT |  |  |  |  | 450 | [7 empty] | 450 | 0.07 | 0 | 0 | 0
125 | 28544 | SO | 10 | TUNDISH DAMAGE PLATE CHANGE REPAIR OF TUNDISH DAMAGE BOTTOM PLATE |  | RAVI RANJAN/SASHI | 2026-02-13 | 2026-12-10 |  | 1100 |  |  | 80 | 1180 |  |  |  |  | 0 | 1100 | 0 | 0 | 80 | 1180 | 1100 | 0 | 0 | 80 | 1180 | OTH | SERVICE | 420 | 340 | 340 | [9 empty] | 1100 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE |  |  |  | 80 | [8 empty] | 80 | 0 | 0 | 0 | 0
126 | 27285 | SO | 6 | EAF FES WATER COOLED SEGMENTS 1-6 | APEX | Rejeesh | 2026-02-16 |  | 93933 | 15390 | 40 |  |  | 15430 |  |  |  |  | 0 | 15390 | 40 | 0 | 0 | 15430 | 0 | 0 | 0 | 0 | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | 15390 | 40 | 0 | 0
127 | 16209 | SO | 4 | REFURBISHMENT OF HYDRAULIC PLUGGING CYLINDER REFURBISHMENT OF DIFFERENTIAL CYLINDER | NA | SANGRAM SWAIN | 2026-02-16 | 2026-10-16 | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | 0 | 0 | 0 | 0
128 | S000982CAS.SCP.STG.BOS | 28310 | 1 | SEGMENT 4-6 LOOSE SIDE ASSEMBLY |  | Kameshwaran | 2026-02-19 | 2026-12-31 |  | 1428 | 360 |  | 300 | 2088 |  |  |  |  | 0 | 1428 | 360 | 0 | 300 | 2088 | 1428 | 360 | 0 | 300 | 2088 | OTH | SERVICE |  |  | 700 | 728 | [8 empty] | 1428 | OTH | SERVICE |  |  |  |  | 180 | 180 | [6 empty] | 360 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [6 empty] | 300 | [5 empty] | 300 | 0 | 0 | 0 | 0
129 | C04MC3PPCM.RLS.TRP.RSCK | WBS | 1 | ROLL TRANSFER CAR |  | AVIJIT SAHA | 2026-02-19 |  | 25000 | 1055 | 75 | 105 | 250 | 1485 |  |  |  |  | 0 | 1055 | 75 | 105 | 250 | 1485 | 1055 | 75 | 105 | 250 | 1485 | OTH | WBS |  | 200 | 300 | 400 | 155 | [7 empty] | 1055 | OTH | WBS |  |  |  |  | 75 | [7 empty] | 75 | OTH | WBS |  |  |  |  | 53 | 52 | [6 empty] | 105 | OTH | WBS | [6 empty] | 250 | [5 empty] | 250 | 0 | 0 | 0 | 0
130 | C04MC3PPCM.RLS.SRG.SGPK | WBS | 44 | STORAGE PAD | NA | AVIJIT SAHA | 2026-02-19 |  | 40000 | 4905 | 30 | 85 | 100 | 5120 |  |  |  |  | 0 | 4905 | 30 | 85 | 100 | 5120 | 0 | 0 | 0 | 0 | 0 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | 4905 | 30 | 85 | 100
131 | C04MC3PPCM.RLS.SRG.SRCK | WBS | 15 | STORAGE RACK |  | AVIJIT SAHA | 2026-02-19 |  | 45000 | 5510 | 50 | 175 | 100 | 5835 |  |  |  |  | 0 | 5510 | 50 | 175 | 100 | 5835 | 5010 | 50 | 175 | 100 | 5335 | OTH | WBS |  |  | 800 | 1200 | 1000 | 2010 | [6 empty] | 5010 | OTH | WBS | [5 empty] | 50 | [6 empty] | 50 | OTH | WBS |  |  |  |  | 75 | 100 | [6 empty] | 175 | OTH | WBS | [6 empty] | 100 | [5 empty] | 100 | 500 | 0 | 0 | 0
132 | C04MC3PPCM.RLS.SRG.SGEK | WBS | 8 | STORAGE CRADLE | NA | AVIJIT SAHA | 2026-02-19 |  | 8000 | 750 | 30 | 50 | 50 | 880 |  |  |  |  | 0 | 750 | 30 | 50 | 50 | 880 | 0 | 0 | 0 | 0 | 0 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | 750 | 30 | 50 | 50
133 | C04MC3PPCM.RLS.SRG.SGVK | WBS | 3 | STORAGE SHELVE | NA | AVIJIT SAHA | 2026-02-19 |  | 2000 | 105 | 5 | 20 | 10 | 140 |  |  |  |  | 0 | 105 | 5 | 20 | 10 | 140 | 0 | 0 | 0 | 0 | 0 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | 105 | 5 | 20 | 10
134 | C04MC3PPCM.RLS.AUX.DECK | WBS | 1 | DECHOCKER (WR) |  | AVIJIT SAHA | 2026-02-19 |  | 15000 | 1870 | 75 | 150 | 250 | 2345 |  |  |  |  | 0 | 1870 | 75 | 150 | 250 | 2345 | 1870 | 75 | 150 | 250 | 2345 | OTH | WBS |  | 200 | 300 | 500 | 870 | [7 empty] | 1870 | OTH | WBS |  |  |  |  | 75 | [7 empty] | 75 | OTH | WBS |  |  |  |  | 150 | [7 empty] | 150 | OTH | WBS | [5 empty] | 250 | [6 empty] | 250 | 0 | 0 | 0 | 0
135 | C0CDA1PCAS1LPC.CPE.LATK | WBS | 1 | LADLE TURRET |  | KRISHNASIS | 2026-02-25 |  | 100000 | 9670 | 540 | 495 | 1500 | 12205 |  |  |  |  | 0 | 9670 | 540 | 495 | 1500 | 12205 | 9670 | 540 | 495 | 1500 | 12205 | OTH | WBS |  |  | 500 | 500 | 1000 | 2470 | 2200 | 3000 |  |  |  |  | 9670 | OTH | WBS | [6 empty] | 270 | 270 |  |  |  |  | 540 | OTH | WBS |  |  |  |  | 248 | 247 | [6 empty] | 495 | OTH | WBS | [6 empty] | 750 | 750 |  |  |  |  | 1500 | 0 | 0 | 0 | 0
136 | C0CDA1PCAS2LPC.CPE.LATK | WBS | 1 | LADLE TURRET |  | KRISHNASIS | 2026-02-25 |  | 100000 | 9670 | 540 | 495 | 1500 | 12205 |  |  |  |  | 0 | 9670 | 540 | 495 | 1500 | 12205 | 9670 | 540 | 495 | 1500 | 12205 | OTH | WBS |  |  |  | 500 | 500 | 900 | 3570 | 2200 | 2000 |  |  |  | 9670 | OTH | WBS | [7 empty] | 270 | 270 |  |  |  | 540 | OTH | WBS | [5 empty] | 248 | 247 | [5 empty] | 495 | OTH | WBS | [7 empty] | 750 | 750 |  |  |  | 1500 | 0 | 0 | 0 | 0
137 | 28233 | SO | 1 | DISTRIBUTOR & ACC. |  | SANGRAM SWAIN | 2026-02-24 | 2026-09-27 | 2996 | 476 | 12 | 14 | 45 | 547 | 114.5 |  |  |  | 114.5 | 361.5 | 12 | 14 | 45 | 432.5 | 361.5 | 12 | 14 | 45 | 432.5 | OTH | SERVICE | 361.5 | [11 empty] | 361.5 | OTH | SERVICE | 12 | [11 empty] | 12 | OTH | SERVICE | 14 | [11 empty] | 14 | OTH | SERVICE | 45 | [11 empty] | 45 | 0 | 0 | 0 | 0
138 | S001004CSP.TSC.MAO.OSC | 28034 | 1 | MOULD OSCILLATION ASSEMBLY |  | KRISHNASIS | 2026-02-26 |  | 17909 | 1572 | 260 | 120 | 450 | 2402 |  |  |  |  | 0 | 1572 | 260 | 120 | 450 | 2402 | 1572 | 260 | 120 | 450 | 2402 | OTH | SERVICE |  | 524 | 524 | 524 | [8 empty] | 1572 | OTH | SERVICE |  |  | 130 | 130 | [8 empty] | 260 | OTH | SERVICE |  |  | 60 | 60 | [8 empty] | 120 | OTH | SERVICE | [5 empty] | 225 | 225 | [5 empty] | 450 | 0 | 0 | 0 | 0
139 | 29297 | SO | 6 | TOP PINCH ROLL & BOTTOM PINCH ROLL |  | AMAN SINGH | 2026-02-26 | 2027-02-20 | 20000 | 2106 | 72 | 480 | 144 | 2802 |  |  |  |  | 0 | 2106 | 72 | 480 | 144 | 2802 | 2106 | 72 | 480 | 144 | 2802 | OTH | SERVICE |  |  | 100 | 100 | 500 | 1406 | [6 empty] | 2106 | OTH | SERVICE |  |  |  |  | 72 | [7 empty] | 72 | OTH | SERVICE |  |  | 240 | 240 | [8 empty] | 480 | OTH | SERVICE |  |  |  | 144 | [8 empty] | 144 | 0 | 0 | 0 | 0
140 | C0COA1PBFP.BLF.TCS.DIRK | WBS | 1 | DISTRIBUTION ROCKER INCLUDING LINERS |  | SANGRAM SWAIN | 2026-02-16 |  |  | 886 | 32 | 94 | 150 | 1162 |  |  |  |  | 0 | 886 | 32 | 94 | 150 | 1162 | 886 | 32 | 94 | 150 | 1162 | OTH | WBS |  | 443 | 443 | [9 empty] | 886 | OTH | WBS |  |  | 32 | [9 empty] | 32 | OTH | WBS |  |  |  | 94 | [8 empty] | 94 | OTH | WBS |  |  |  |  | 150 | [7 empty] | 150 | 0 | 0 | 0 | 0
141 | C0COA1PBFP.BLF.TCS.VAUK | WBS | 1 | LOWER VALVE ACTUATION UNIT & ACCESSORIES |  | SANGRAM SWAIN | 2026-02-16 |  |  | 4041 | 200 | 350 | 350 | 4941 |  |  |  |  | 0 | 4041 | 200 | 350 | 350 | 4941 | 4041 | 400 | 520 | 700 | 5661 | OTH | WBS |  |  |  | 1000 | 1000 | 1000 | 1041 | [5 empty] | 4041 | OTH | WBS | [5 empty] | 200 | 200 | [5 empty] | 400 | OTH | WBS | [5 empty] | 260 | 260 | [5 empty] | 520 | OTH | WBS | [5 empty] | 350 | 350 | [5 empty] | 700 | 0 | -200 | -170 | -350
142 | C0COA1PBFP.BLF.TCS.MAHK | WBS | 2 | MATERIAL HOPPER (2 NOS) & ACCESSORIES |  | SANGRAM SWAIN | 2026-02-16 |  |  | 9000 | 200 | 200 | 280 | 9680 |  |  |  |  | 0 | 9000 | 200 | 200 | 280 | 9680 | 9000 | 200 | 200 | 280 | 9680 | OTH | WBS |  |  |  | 2000 | 2000 | 2000 | 1000 | 2000 |  |  |  |  | 9000 | OTH | WBS | [6 empty] | 100 | 100 |  |  |  |  | 200 | OTH | WBS | [5 empty] | 100 | 100 | [5 empty] | 200 | OTH | WBS | [7 empty] | 280 |  |  |  |  | 280 | 0 | 0 | 0 | 0
143 | C0COA1PBFP.BLF.TGS.BLEK | WBS | 4 | BLEEDER VALVE & ACCESSORIES |  | SANGRAM SWAIN | 2026-02-16 |  |  | 2182 | 140 | 102 | 800 | 3224 |  |  |  |  | 0 | 2182 | 140 | 102 | 800 | 3224 | 2182 | 140 | 102 | 800 | 3224 | OTH | WBS |  | 546 | 546 | 545 | 545 | [7 empty] | 2182 | OTH | WBS |  |  |  |  | 140 | [7 empty] | 140 | OTH | WBS |  |  |  |  | 102 | [7 empty] | 102 | OTH | WBS | [5 empty] | 400 | 400 | [5 empty] | 800 | 0 | 0 | 0 | 0
144 | C0COA1PBFP.BLF.TGS.BLEK | WBS | 4 | ADAPTER FLANGES FOR BLEEDER VALVES | NA | SANGRAM SWAIN | 46069
145 | C0COA1PBFP.SGR.DEW.DRUK | WBS | 2 | DEWATERING DRUM |  | SANGRAM SWAIN | 2026-02-16 |  |  | 8304 | 440 | 210 |  | 8954 | 1748 | 28 | 19 | 17 | 1812 | 6556 | 412 | 191 | -17 | 7142 | 6556 | 412 | 191 | 0 | 7159 | OTH | WBS | 900 | 985 | 800 | 1000 | 2871 | [7 empty] | 6556 | OTH | WBS | 100 | 100 | 212 | [9 empty] | 412 | OTH | WBS |  | 96 | 95 | [9 empty] | 191 | OTH | WBS | [12 empty] | 0 | 0 | 0 | 0 | -17
146 | C0COA1PBFP.SGR.DEW.DSUK | WBS | 2 | DEWATERING DRUM SUPPORT+ PILLOW BLOCK - + DRIVE WHEELS |  | SANGRAM SWAIN | 2026-02-16 |  |  | 2259 | 32 | 40 | 300 | 2631 |  |  |  |  | 0 | 2259 | 32 | 40 | 300 | 2631 | 2259 | 32 | 40 | 300 | 2631 | OTH | WBS |  |  | 565 | 564 | 565 | 565 | [6 empty] | 2259 | OTH | WBS | [5 empty] | 32 | [6 empty] | 32 | OTH | WBS | [5 empty] | 40 | [6 empty] | 40 | OTH | WBS | [5 empty] | 150 | 150 | [5 empty] | 300 | 0 | 0 | 0 | 0
147 | 29620 | SO | 20 | TIGHTENER ARRANGEMENT |  | SANGRAM SWAIN | 2026-03-02 | 2026-10-07 | 4314 |  |  |  | 40 | 40 |  |  |  | 32 | 32 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | 0 | 0 | 0 | 8
148 | 29716 | SO | 2 | SPARE KIT FOR 32" SUB BY-PASS VALVE SPARE KIT FOR 64" MAIN BY-PASS VALVE |  | SANGRAM SWAIN | 2026-03-03 | 2026-11-28 | 900 |  |  | 20 |  | 20 |  |  |  |  | 0 | 0 | 0 | 20 | 0 | 20 | 0 | 0 | 20 | 0 | 20 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE |  |  |  |  | 20 | [7 empty] | 20 | OTH | SERVICE | [12 empty] | 0 | 0 | 0 | 0 | 0
149 | C0COA1PBFP.BLF.PES.VGO1K | WBS | 16 | GOGGLE VALVE ND500 |  | SANGRAM SWAIN | 2026-03-06 | 2026-11-28 | 15000 | 4702 | 1920 | 2208 | 3520 | 12350 |  |  |  |  | 0 | 4702 | 1920 | 2208 | 3520 | 12350 | 4462 | 1920 | 2208 | 3520 | 12110 | OTH | WBS | 600 | 1522 | 1000 | 400 | 940 | [7 empty] | 4462 | OTH | WBS |  |  | 640 | 640 | 640 | [7 empty] | 1920 | OTH | WBS |  |  | 736 | 736 | 736 | [7 empty] | 2208 | OTH | WBS |  |  |  | 650 | 2000 | 870 | [6 empty] | 3520 | 240 | 0 | 0 | 0
150 | S001094SMP.GCP.CSS.COS | 25469 | 9 | SKIRT, MOVABLE HOOD & LANCE DOME |  | Rejeesh | 2026-03-10 | 2026-12-16 | 22000 | 11405.7 |  | 34 |  | 11439.7 |  |  |  |  | 0 | 11405.7 | 0 | 34 | 0 | 11439.7 | 11406 | 0 | 34 | 0 | 11440 | OTH | SERVICE | 400 | 900 | 900 | 1901 | 1901 | 2200 | 2200 | 1004 |  |  |  |  | 11406 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [5 empty] | 34 | [6 empty] | 34 | OTH | SERVICE | [12 empty] | 0 | -0.3 | 0 | 0 | 0
151 | 30276 | SO | 34 | FS SWIVEL ARM, BRACKET |  | BALLA RANI | 2026-03-09 | 2026-08-31 | 3730 | 615 | 123 | 350 |  | 1088 | 441.63 |  |  |  | 441.63 | 173.37 | 123 | 350 | 0 | 646.37 | 173 | 123 | 350 | 0 | 646 | OTH | DIRECT | 173 | [11 empty] | 173 | OTH | DIRECT |  |  | 123 | [9 empty] | 123 | OTH | DIRECT |  |  | 350 | [9 empty] | 350 | OTH | DIRECT | [12 empty] | 0 | 0.37 | 0 | 0 | 0
152 | 29232 | SO | 2 | DISTRIBUTION CHUTE & CONICAL CHUTE ND1000 & ACC. |  | SANGRAM SWAIN | 2026-03-11 | 2026-11-03 | 9620 | 750 |  | 40 | 60 | 850 | 3.2 |  |  |  | 3.2 | 746.8 | 0 | 40 | 60 | 846.8 | 747 | 0 | 40 | 60 | 847 | OTH | SERVICE | 187 | 187 | 187 | 186 | [8 empty] | 747 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE |  |  |  |  | 40 | [7 empty] | 40 | OTH | SERVICE | [5 empty] | 60 | [6 empty] | 60 | -0.2 | 0 | 0 | 0
153 | C04MC3PPCM.RLS.AUX.DEC2K | WBS | 1 | DECHOCKER (BUR) |  | AVIJIT SAHA |  |  | 20000 | 2570 | 75 | 150 | 250 | 3045 |  |  |  |  | 0 | 2570 | 75 | 150 | 250 | 3045 | 2570 | 75 | 150 | 250 | 3045 | OTH | WBS |  | 600 | 700 | 700 | 570 | [7 empty] | 2570 | OTH | WBS |  |  |  |  | 75 | [7 empty] | 75 | OTH | WBS |  |  |  |  | 150 | [7 empty] | 150 | OTH | WBS | [5 empty] | 250 | [6 empty] | 250 | 0 | 0 | 0 | 0
154 | C04MC3PPCM.RLS.AUX.CKTK | WBS | 1 | CHOCK TILTER |  | AVIJIT SAHA |  |  | 20000 | 2066 | 270 | 390 | 300 | 3026 |  |  |  |  | 0 | 2066 | 270 | 390 | 300 | 3026 | 2066 | 270 | 390 | 300 | 3026 | OTH | WBS |  | 517 | 517 | 516 | 516 | [7 empty] | 2066 | OTH | WBS |  |  |  |  | 100 | 170 | [6 empty] | 270 | OTH | WBS |  |  |  |  | 190 | 200 | [6 empty] | 390 | OTH | WBS | [6 empty] | 300 | [5 empty] | 300 | 0 | 0 | 0 | 0
155 | C04MC3PPCM.RLS.AUX.BECK | WBS | 1 | CHOCK & BEARING CLEANING MACHINE |  | AVIJIT SAHA |  |  |  | 510 | 40 |  | 60 | 610 |  |  |  |  | 0 | 510 | 40 | 0 | 60 | 610 | 510 | 40 | 0 | 60 | 610 | OTH | WBS |  | 128 | 128 | 127 | 127 | [7 empty] | 510 | OTH | WBS |  |  |  |  | 20 | 20 | [6 empty] | 40 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [6 empty] | 60 | [5 empty] | 60 | 0 | 0 | 0 | 0
156 | C04MC3PPCM.RLS.AUX.RCLK | WBS | 1 | ROLL CLEANING STATION |  | AVIJIT SAHA | [6 empty] | 50 | 50 |  |  |  |  | 0 | 0 | 0 | 0 | 50 | 50 | 0 | 0 | 0 | 50 | 50 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [6 empty] | 50 | [5 empty] | 50 | 0 | 0 | 0 | 0
157 | 29619 | SO | 1 | REFURBISHMENT OF DISTRIBUTION CHUTE |  | SANGRAM SWAIN | 2026-03-17 | 2026-07-31 |  |  | 20 |  | 200 | 220 |  |  |  | 97 | 97 | 0 | 20 | 0 | 103 | 123 | 0 | 20 | 0 | 103 | 123 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | 20 | [11 empty] | 20 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | 103 | [11 empty] | 103 | 0 | 0 | 0 | 0
158 | 26277 | SO | 2 | SPARES FOR DRIVE OF LSV/USV | NA | SANGRAM SWAIN | 2026-03-18 | 2026-08-10 | [5 empty] | 0 |  |  |  | 0.5 | 0.5 | 0 | 0 | 0 | -0.5 | -0.5 | 0 | 0 | 0 | 0 | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | 0 | 0 | 0 | -0.5
159 | 30513 | SO | 2 | SLOWDOWN BOX & DISTRIBUTOR |  | SANGRAM SWAIN | 2026-03-19 | 2026-10-20 | 5278 | 568 | 8 |  |  | 576 |  |  |  |  | 0 | 568 | 8 | 0 | 0 | 576 | 568 | 8 | 0 | 0 | 576 | OTH | SERVICE |  |  | 284 | 284 | [8 empty] | 568 | OTH | SERVICE |  |  |  |  | 8 | [7 empty] | 8 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | 0 | 0 | 0 | 0
160 | 30585 | SO | 9 | DRIVE DR & ACC |  | SANGRAM SWAIN | 2026-03-19 | 2026-11-13 |  | 128 |  | 8 | 100 | 236 |  |  |  |  | 0 | 128 | 0 | 8 | 100 | 236 | 128 | 0 | 8 | 100 | 236 | OTH | SERVICE |  |  | 128 | [9 empty] | 128 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE |  |  |  | 8 | [8 empty] | 8 | OTH | SERVICE | [5 empty] | 100 | [6 empty] | 100 | 0 | 0 | 0 | 0
161 | 29536 | SO | 12 | REFURBISHMENT OF BD MILL CHOCK |  | Sambit Sahoo | 2026-03-19 | 2026-12-30 |  |  |  |  | 150 | 150 |  |  |  |  | 0 | 0 | 0 | 0 | 150 | 150 | 0 | 0 | 0 | 150 | 150 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [5 empty] | 150 | [6 empty] | 150 | 0 | 0 | 0 | 0
162 | 30721 | SO |  | ACESSORIES FOR TWIN LF ROOF | APEX | Rejeesh | 2026-03-20 | 2026-04-20 | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OTH | DIRECT | [12 empty] | 0 | OTH | DIRECT | [12 empty] | 0 | OTH | DIRECT | [12 empty] | 0 | OTH | DIRECT | [12 empty] | 0 | 0 | 0 | 0 | 0
163 | C094B1PCSP.TSC.STG.VSE1K | WBS | 1 | UPPER VERTICAL SEGMENT - SEG#1-MAIN |  | RAVI RANJAN | 2026-03-20 | 2027-03-01 | 16000 | 1000 | 250 |  | 350 | 1600 |  |  |  |  | 0 | 1000 | 250 | 0 | 350 | 1600 | 1000 | 250 | 0 | 350 | 1600 | OTH | WBS | [5 empty] | 300 | 300 | 300 | 100 |  |  |  | 1000 | OTH | WBS | [7 empty] | 100 | 150 |  |  |  | 250 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [9 empty] | 350 |  |  | 350 | 0 | 0 | 0 | 0
164 | C094B1SOCPCSPSTG.VSE801K | WBS | 3 | UPPER VERTICAL SEGMENT (OCP) - SEG#1 - SPARE |  | RAVI RANJAN | 2026-03-20 | 2027-01-29 | 20000 | 3000 | 750 |  | 720 | 4470 |  |  |  |  | 0 | 3000 | 750 | 0 | 720 | 4470 | 3000 | 750 | 0 | 720 | 4470 | OTH | WBS |  |  | 600 | 600 | 600 | 600 | 600 | [5 empty] | 3000 | OTH | WBS | [5 empty] | 375 | 375 | [5 empty] | 750 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [7 empty] | 360 | 360 |  |  |  | 720 | 0 | 0 | 0 | 0
165 | C094B1PCSP.TSC.STG.VSE2K | WBS | 1 | INTERMEDIATE VERTICAL SEGMENT - SEG#2 - MAIN |  | RAVI RANJAN | 2026-03-20 | 2027-03-01 | 18747 | 1100 | 250 |  | 350 | 1700 |  |  |  |  | 0 | 1100 | 250 | 0 | 350 | 1700 | 1100 | 250 | 0 | 350 | 1700 | OTH | WBS | [5 empty] | 300 | 300 | 300 | 200 |  |  |  | 1100 | OTH | WBS | [7 empty] | 100 | 150 |  |  |  | 250 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [9 empty] | 350 |  |  | 350 | 0 | 0 | 0 | 0
166 | C094B1SOCPCSPSTG.VSE802K | WBS | 2 | INTERMEDIATE VERTICAL SEGMENT (OCP) - SEG#2 - SPARE |  | RAVI RANJAN | 2026-03-20 | 2027-01-29 | 15000 | 2200 | 500 |  | 560 | 3260 |  |  |  |  | 0 | 2200 | 500 | 0 | 560 | 3260 | 2200 | 500 | 0 | 560 | 3260 | OTH | WBS |  |  | 500 | 500 | 400 | 400 | 400 | [5 empty] | 2200 | OTH | WBS | [5 empty] | 250 | 250 | [5 empty] | 500 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [6 empty] | 280 | 280 |  |  |  |  | 560 | 0 | 0 | 0 | 0
167 | C094B1PCSP.TSC.STG.VSE3K | WBS | 1 | LOWER VERTICAL SEGMENT - SEG# 3 - MAIN |  | RAVI RANJAN | 2026-03-20 | 2027-02-18 | 15000 | 1700 | 375 |  | 360 | 2435 |  |  |  |  | 0 | 1700 | 375 | 0 | 360 | 2435 | 1700 | 375 | 0 | 360 | 2435 | OTH | WBS |  |  | 340 | 340 | 340 | 340 | 340 | [5 empty] | 1700 | OTH | WBS | [6 empty] | 188 | 187 |  |  |  |  | 375 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [8 empty] | 360 |  |  |  | 360 | 0 | 0 | 0 | 0
168 | C094B1PCSP.TSC.STG.VSE4K | WBS | 1 | LOWER VERTICAL SEGMENT - SEG# 4 -MAIN |  | RAVI RANJAN | 2026-03-20 | 2027-01-29 | 15000 | 1700 | 375 |  | 360 | 2435 |  |  |  |  | 0 | 1700 | 375 | 0 | 360 | 2435 | 1700 | 375 | 0 | 360 | 2435 | OTH | WBS |  | 340 | 340 | 340 | 340 | 340 | [6 empty] | 1700 | OTH | WBS |  |  |  |  | 188 | 187 | [6 empty] | 375 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [6 empty] | 100 | 260 |  |  |  |  | 360 | 0 | 0 | 0 | 0
169 | C094B1SOCPCSPSTG.VSE803K | WBS | 1 | LOWER VERTICAL SEGMENT - (OCP) -SEG# 3 - SPARE |  | RAVI RANJAN | 2026-03-20 | 2027-03-01 | 15000 | 1700 | 375 |  | 360 | 2435 |  |  |  |  | 0 | 1700 | 375 | 0 | 360 | 2435 | 1700 | 375 | 0 | 360 | 2435 | OTH | WBS |  |  | 340 | 340 | 340 | 340 | 340 | [5 empty] | 1700 | OTH | WBS | [7 empty] | 188 | 187 |  |  |  | 375 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [9 empty] | 360 |  |  | 360 | 0 | 0 | 0 | 0
170 | C094B1SOCPCSPSTG.VSE804K | WBS | 1 | LOWER VERTICAL SEGMENT - (OCP) - SEG# 4 - SPARE |  | RAVI RANJAN | 2026-03-20 | 2027-01-29 | 15000 | 1700 | 375 |  | 360 | 2435 |  |  |  |  | 0 | 1700 | 375 | 0 | 360 | 2435 | 1700 | 375 | 0 | 360 | 2435 | OTH | WBS |  | 340 | 340 | 340 | 340 | 340 | [6 empty] | 1700 | OTH | WBS |  |  |  |  | 188 | 187 | [6 empty] | 375 | OTH | WBS | [12 empty] | 0 | OTH | WBS | [6 empty] | 100 | 260 |  |  |  |  | 360 | 0 | 0 | 0 | 0
171 | 30779 | SO | 6 | UPRIGHT LEFT UPRIGHT RIGHT |  | BALLA RANI | 2026-03-23 | 2026-09-15 | 4048 | 1215 | 81 | 250 |  | 1546 | 1808 |  |  |  | 1808 | -593 | 81 | 250 | 0 | -262 | 0 | 81 | 250 | 0 | 331 | OTH | DIRECT | [12 empty] | 0 | OTH | DIRECT |  |  | 81 | [9 empty] | 81 | OTH | DIRECT |  |  |  | 100 | 150 | [7 empty] | 250 | OTH | DIRECT | [12 empty] | 0 | -593 | 0 | 0 | 0
172 | 29618 | SO |  | ACESSORIES FOR PROJECT | APEX | Rejeesh | [7 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OTH | DIRECT | [12 empty] | 0 | OTH | DIRECT | [12 empty] | 0 | OTH | DIRECT | [12 empty] | 0 | OTH | DIRECT | [12 empty] | 0 | 0 | 0 | 0 | 0
173 | 30015 | SO | 28 | INJECTION LANCE ASSEMBLY |  | SANGRAM SWAIN | 2026-03-24 | 2026-10-25 | 5278 |  |  |  | 112 | 112 |  |  |  |  | 0 | 0 | 0 | 0 | 112 | 112 | 0 | 0 | 0 | 112 | 112 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE |  |  |  |  | 112 | [7 empty] | 112 | 0 | 0 | 0 | 0
174 | 30133 | SO | 15 | COAL INJECTION LANCE |  | SANGRAM SWAIN | 2026-03-25 | 2026-11-23 | 1148 |  |  |  | 15 | 15 |  |  |  |  | 0 | 0 | 0 | 0 | 15 | 15 | 0 | 0 | 0 | 15 | 15 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [5 empty] | 15 | [6 empty] | 15 | 0 | 0 | 0 | 0
175 |  | SO | 1 | MATERIAL ANALYSIS |  | RAVI RANJAN | 2026-03-26 | [6 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OTH | DIRECT | [12 empty] | 0 | OTH | DIRECT | [12 empty] | 0 | OTH | DIRECT | [12 empty] | 0 | OTH | DIRECT | [12 empty] | 0 | 0 | 0 | 0 | 0
176 | 30493 | SO | 1 | INBA PERFORATED PLATE ASSEMBLY |  | SANGRAM SWAIN | 2026-03-27 | 2026-09-12 |  |  |  |  | 8 | 8 |  |  |  |  | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | 0 | 0 | 0 | 8
177 | 27003 | SO | 1 | SPARE KIT FOR DC | NA | SANGRAM SWAIN | 2026-03-30 | 2026-09-13 | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | 0 | 0 | 0 | 0
178 | 30941 | SO | 1 | GOGGLE VALVE ND500 PN10 |  | SANGRAM SWAIN | 2026-03-31 | 2026-11-12 |  |  |  |  | 20 | 20 |  |  |  |  | 0 | 0 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | 0 | 0 | 0 | 20
179 | 30488 | SO | 28 | Spare JSW BELLARY COPPER JOB |  | KRISHNASIS | 2026-03-30 |  |  | 2100 | 450 |  |  | 2550 |  |  |  |  | 0 | 2100 | 450 | 0 | 0 | 2550 | 2100 | 450 | 0 | 0 | 2550 | OTH | SERVICE |  |  | 525 | 525 | 525 | 525 | [6 empty] | 2100 | OTH | SERVICE |  |  |  | 225 | 225 | [7 empty] | 450 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | 0 | 0 | 0 | 0
180 | 25991 | SO | 1 | REFURBISHMENT OF GRITZKO VALVE |  | SANGRAM SWAIN | 2026-03-12 | 2026-12-11 |  |  |  | 10 | 125 | 135 |  |  |  | 75 | 75 | 0 | 0 | 10 | 50 | 60 | 0 | 0 | 0 | 50 | 50 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [5 empty] | 50 | [6 empty] | 50 | 0 | 0 | 10 | 0
181 | S001071SMP.FTP.WCG.COH | 31367 | 2 | COMBUSTION CHAMBER & MOVABLE ELBOW |  | Rejeesh | 2026-04-02 | 2027-07-31 |  | 28480 |  |  |  | 28480 |  |  |  |  | 0 | 28480 | 0 | 0 | 0 | 28480 | 28480 | 0 | 0 | 0 | 28480 | Group | DIRECT |  | 200 | 200 | 1000 | 5300 | 6300 | 6050 | 8980 | 450 |  |  |  | 28480 | Group | DIRECT | [12 empty] | 0 | Group | DIRECT | [12 empty] | 0 | Group | DIRECT | [12 empty] | 0 | 0 | 0 | 0 | 0
182 | 31025 | SO | 2 | WEAR PLATE ASSEMBLY |  | SANGRAM SWAIN | 2026-04-01 | 2026-12-21 | 7960 |  |  |  | 20 | 20 |  |  |  |  | 0 | 0 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 20 | 20 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [5 empty] | 20 | [6 empty] | 20 | 0 | 0 | 0 | 0
183 | 31208 | SO | 1 | SPARE KIT FOR HBV |  | SANGRAM SWAIN | 2026-04-01 | 2026-12-26 | 10000 |  |  |  | 40 | 40 |  |  |  |  | 0 | 0 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 40 | 40 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [5 empty] | 40 | [6 empty] | 40 | 0 | 0 | 0 | 0
184 | 30291 | SO | 8 | DEFLECTORS, RAIL & SLOW DOWN BOX |  | SANGRAM SWAIN | 2026-04-02 | 2026-09-26 | 10000 | 1010 | 104 | 180 |  | 1294 |  |  |  |  | 0 | 1010 | 104 | 180 | 0 | 1294 | 1010 | 104 | 180 | 0 | 1294 | OTH | SERVICE | 253 | 253 | 252 | 252 | [8 empty] | 1010 | OTH | SERVICE |  |  |  |  | 104 | [7 empty] | 104 | OTH | SERVICE |  |  |  |  | 180 | [7 empty] | 180 | OTH | SERVICE | [12 empty] | 0 | 0 | 0 | 0 | 0
185 | 22452 | SO | 10 | BLOWPIPE ASSEMBLY |  | SANGRAM SWAIN | 2025-09-26 | 2025-12-31 | 3500 |  |  |  | 120 | 120 |  |  |  | 74.8 | 74.8 | 0 | 0 | 0 | 45.2 | 45.2 | 0 | 0 | 0 | 45 | 45 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [5 empty] | 45 | [6 empty] | 45 | 0 | 0 | 0 | 0.2
186 | A03314M431.86P0300 | WBS | 1 | ADJUSTABLE SKIRT |  | Rejeesh | 2026-04-15 | 2026-12-31 | 9167 | 2023 |  | 14 |  | 2037 |  |  |  |  | 0 | 2023 | 0 | 14 | 0 | 2037 | 2023 | 0 | 14 | 0 | 2037 | Group | WBS |  |  |  | 405 | 405 | 404 | 404 | 405 |  |  |  |  | 2023 | Group | WBS | [12 empty] | 0 | Group | WBS | [5 empty] | 14 | [6 empty] | 14 | Group | WBS | [12 empty] | 0 | 0 | 0 | 0 | 0
187 | 31141 | SO | 4 | WR CHOCK |  | Kameshwaran | 2026-04-10 | 2026-12-31 | 10000 | 26 | 614 | 208 |  | 848 |  |  |  |  | 0 | 26 | 614 | 208 | 0 | 848 | 26 | 614 | 0 | 0 | 640 | OTH | SERVICE |  |  |  | 26 | [8 empty] | 26 | OTH | SERVICE | [5 empty] | 300 | 314 | [5 empty] | 614 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | 0 | 0 | 208 | 0
188 | 31827 | SO | 20 | BLOWPIPE TIGHTENER ARRGMNT |  | SANGRAM SWAIN | 2026-04-14 | 2026-10-10 | 3600 |  |  |  | 40 | 40 |  |  |  |  | 0 | 0 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 40 | 40 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE |  |  |  |  | 40 | [7 empty] | 40 | 0 | 0 | 0 | 0
189 | A03080M431.86.20P2000 | WBS | 2 | FLUX CHUTE |  | Rejeesh | 2026-04-17 |  | 2858.6 | 837 |  |  |  | 837 | 400 |  |  |  | 400 | 437 | 0 | 0 | 0 | 437 | 437 | 0 | 0 | 0 | 437 | Group | WBS | 200 | 237 | [10 empty] | 437 | Group | WBS | [12 empty] | 0 | Group | WBS | [12 empty] | 0 | Group | WBS | [12 empty] | 0 | 0 | 0 | 0 | 0
190 | 32095 | SO | 1 | FEEDER SPOUT |  | SANGRAM SWAIN | 2026-04-17 | 2026-05-31 | 1510 | 221 | 40 | 28 | 200 | 489 | 50.62 | 57.5 | 9 |  | 117.12 | 170.38 | -17.5 | 19 | 200 | 371.88 | 0 | 0 | 0 | 0 | 0 | OTH | DIRECT | [12 empty] | 0 | OTH | DIRECT | [12 empty] | 0 | OTH | DIRECT | [12 empty] | 0 | OTH | DIRECT | [12 empty] | 0 | 170.38 | -17.5 | 19 | 200
191 | 31917 | SO | 1 | CYLINDER BARREL | NA | SHASHIKUMAR | 2026-04-17 | 2026-12-31 | 730 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | OTH | SERVICE | [12 empty] | 0 | 0 | 0 | 0 | 0
192 | 32001 | SO | 1 | DRAWING DEVELOPMENT OF VC COVER HOOD |  | RAVI RANJAN | 2026-04-16 | 2026-10-07 | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OTH | DIRECT | [12 empty] | 0 | OTH | DIRECT | [12 empty] | 0 | OTH | DIRECT | [12 empty] | 0 | OTH | DIRECT | [12 empty] | 0 | 0 | 0 | 0 | 0
193 | S001126PEP.BAS.MAB | 32438 | 1 | DRIVING & TIPING STATION |  | BALLA RANI | 2026-04-20 | 2027-01-15 | 60000 | 4754 | 306 | 355 | 300 | 5715 |  |  |  |  | 0 | 4754 | 306 | 355 | 300 | 5715 | 4754 | 306 | 355 | 300 | 5715 | OTH | DIRECT | 200 | 400 | 362 | 792 | 1500 | 1500 | [6 empty] | 4754 | OTH | DIRECT |  |  |  |  | 150 | 156 | [6 empty] | 306 | OTH | DIRECT |  |  |  |  | 178 | 177 | [6 empty] | 355 | OTH | DIRECT | [6 empty] | 150 | 150 |  |  |  |  | 300 | 0 | 0 | 0 | 0
206 | S001100HPR.FMI.MIS.WOX1 S001100HPR.FMI.MIS.WOX2 | 34836 |  | WORK ROLL CHOCK |  | Kameshwaran | 2026-06-03 | 2027-03-19 | 35000 |  | 1656 | 1426 | 330 | 3412 |  |  |  |  | 0 | 0 | 1656 | 1426 | 330 | 3412 | 0 | 1656 | 1426 | 330 | 3412 | Group | DIRECT | [12 empty] | 0 | Group | DIRECT | [5 empty] | 414 | 414 | 414 | 414 |  |  |  | 1656 | Group | DIRECT | [5 empty] | 372 | 372 | 371 | 311 |  |  |  | 1426 | Group | DIRECT | [8 empty] | 170 | 160 |  |  | 330 | 0 | 0 | 0 | 0
207 |  |  |  | Converter vessel | [5 empty] | 15000 |  | 150 |  | 15150 |  |  |  |  | 0 | [10 empty] | OTH | DIRECT | [8 empty] | 3750 | 3750 | 3750 | 3750 | 15000 | OTH | DIRECT | [12 empty] | 0 | OTH | DIRECT | [10 empty] | 150 |  | 150 | OTH | DIRECT | [12 empty] | 0 | 0 | 0 | 0 | 0
[11 empty] | 10000 | 20000 | 1800 | 31800 |  |  |  |  | 0 | 0 | 10000 | 20000 | 1800 | 31800 | 0 | 10000 | 20000 | 1800 | 31800 | [14 empty] | 0 | TS |  | 250 | 1000 | 1000 | 350 | 50 | 500 | 1000 | 1000 | 1000 | 1000 | 1000 | 1850 | 10000 | TS |  | 1600 | 1600 | 1600 | 1600 | 1500 | 1500 | 1500 | 1500 | 1500 | 1236 | 2432 | 2432 | 20000 | TS |  | 30 | 40 | 250 | 300 | 280 | 200 | 200 | 100 | 100 | 100 | 100 | 100 | 1800 | 0 | 0 | 0 | 0
[13 empty] | 13820 | 13820 |  |  |  |  | 0 | 0 | 0 | 0 | 13820 | 13820 | 0 | 0 | 0 | 13820 | 13820 | [45 empty] | IRON MAKING |  | 900 | 2200 | 3350 | 3500 | 2200 | 500 |  | 670 | 500 |  |  |  | 13820 | 0 | 0 | 0 | 0
GRAND TOTAL | [8 empty] | 4306968.1 | 591957.1456 | 40186 | 38683.7 | 56386 | 727212.8456 | 248182.196 | 13557.83 | 20228.51 | 16025 | 298007.536 | 328774.9496 | 26628.17 | 18305.19 | 40361 | 414069.3096 | 331663.5 | 31409.5 | 37025 | 45675 | 445773 |  |  | 49831.25 | 49026.75 | 47313.75 | 44617.75 | 44183.5 | 41776.5 | 24975 | 20989 | 9300 | 6550 | 4050 | 4050 | 346663.5 |  |  | 3521 | 3493.5 | 3630 | 2786 | 3036 | 3106 | 3177 | 2639 | 2171 | 1000 | 1000 | 1850 | 31409.5 |  |  | 4954 | 3299 | 4514 | 3754 | 4599 | 3444 | 2579 | 1971 | 1811 | 1236 | 2582 | 2432 | 37175 |  |  | 5418 | 5533 | 5528 | 5604 | 5532 | 4775 | 4765 | 4160 | 2540 | 1620 | 100 | 100 | 45675
[30 empty] | NPK |  | 50107.8822 | 51778.1449 | 51778.1449 | 50107.8822 | 51778.1449 | 50107.8822 | 51778.1449 | 51778.1449 | 46767.3567 | 51778.1449 | 50107.8822 | 51778.1449 |  | NPK |  | 8737.4818 | 9028.7312 | 9028.7312 | 8737.4818 | 9028.7312 | 8737.4818 | 9028.7312 | 9028.7312 | 8154.983 | 9028.7312 | 8737.4818 | 9028.7312 |  | NPK |  | 8737.4818 | 9028.7312 | 9028.7312 | 8737.4818 | 9028.7312 | 8737.4818 | 9028.7312 | 9028.7312 | 8154.983 | 9028.7312 | 8737.4818 | 9028.7312 |  | NPK |  | 5423.5479 | 5604.3329 | 5604.3329 | 5423.5479 | 5604.3329 | 5423.5479 | 5604.3329 | 5604.3329 | 5061.9781 | 5604.3329 | 5423.5479 | 5604.3329
[32 empty] | 99.45% | 94.69% | 91.38% | 89.04% | 85.33% | 83.37% | 48.23% | 40.54% | 19.89% | 12.65% | 8.083% | 7.822% |  |  |  | 40.3% | 38.69% | 40.2% | 31.89% | 33.63% | 35.55% | 35.19% | 29.23% | 26.62% | 11.08% | 11.44% | 20.49% |  |  |  | 56.7% | 36.54% | 50% | 42.96% | 50.94% | 39.42% | 28.56% | 21.83% | 22.21% | 13.69% | 29.55% | 26.94% |  |  |  | 99.9% | 98.73% | 98.64% | 103.3% | 98.71% | 88.04% | 85.02% | 74.23% | 50.18% | 28.91% | 1.844% | 1.784%

## SUMMARY-CP
SUMMARY
Sl No | Planned | Total Planned Hour | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-02 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01
1.1 | OTHERS ORDERS | 190236.5 | 30360.25 | 28711.75 | 28053.25 | 24906.25 | 20174 | 17836 | 12591 | 9104 | 6350 | 4050 | 4050 | 4050
1.2 | GROUP COMPANY | 122796 | 14938.5 | 15175.5 | 14938.5 | 16142.5 | 20441.5 | 21440.5 | 9884 | 9385 | 450 | 0 | 0 | 0
1.3 | CONTRACT MANUFACTURING | 33631 | 4532.5 | 5139.5 | 4322 | 3569 | 3568 | 2500 | 2500 | 2500 | 2500 | 2500 | 0 | 0
1 | TOTAL WELDING | 346663.5 | 49831.25 | 49026.75 | 47313.75 | 44617.75 | 44183.5 | 41776.5 | 24975 | 20989 | 9300 | 6550 | 4050 | 4050
2.1 | OTHERS ORDERS | 29134.5 | 5035 | 2557.5 | 4425 | 3619 | 5507 | 3565 | 2304 | 1215 | 757 | 0 | 150 | 0
2.2 | TS | 30000 | 1850 | 2600 | 2600 | 1950 | 1550 | 2000 | 2500 | 2500 | 2500 | 2236 | 3432 | 4282
2.3 | GROUP COMPANY | 5587 | 327 | 327 | 652 | 711 | 418 | 800 | 842 | 785 | 725 | 0 | 0 | 0
2.4 | CONTRACT MANUFACTURING | 3863 | 1263 | 1308 | 467 | 260 | 160 | 185 | 110 | 110 | 0 | 0 | 0 | 0
2 | TOTAL MACHINING | 68584.5 | 8475 | 6792.5 | 8144 | 6540 | 7635 | 6550 | 5756 | 4610 | 3982 | 2236 | 3582 | 4282
3.1 | OTHERS ORDERS | 25176 | 3308 | 2224 | 1928 | 1754 | 2302 | 3775 | 4265 | 3090 | 1470 | 1060 | 0 | 0
3.2 | GROUP COMPANY | 780 | 0 | 0 | 0 | 0 | 450 | 0 | 0 | 0 | 170 | 160 | 0 | 0
3.3 | CONTRACT MANUFACTURING | 4099 | 1180 | 1069 | 0 | 50 | 300 | 300 | 300 | 300 | 300 | 300 | 0 | 0
3.4 | ASSEMBLY-Hydraulic Test Stand | 60 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0
3.5 | TS | 1800 | 30 | 40 | 250 | 300 | 280 | 200 | 200 | 100 | 100 | 100 | 100 | 100
3.6 | IRON MAKING | 13820 | 900 | 2200 | 3350 | 3500 | 2200 | 500 | 0 | 670 | 500 | 0 | 0 | 0
3 | TOTAL ASSEMBLY | 45735 | 5428 | 5543 | 5538 | 5614 | 5542 | 4785 | 4765 | 4160 | 2540 | 1620 | 100 | 100
4 | SERVICE-ROLL REFURBISHMENT | 15276 | 1800 | 1600 | 1500 | 1400 | 1300 | 1200 | 1100 | 1100 | 1100 | 1176 | 1000 | 1000
5 | SERVICE-PLATING | 10260 | 1300 | 1300 | 1200 | 1000 | 1000 | 890 | 800 | 700 | 600 | 500 | 500 | 470
| TOTAL MANUFACTRING | 486519 | 66834.25 | 64262.25 | 63695.75 | 59171.75 | 59660.5 | 55201.5 | 37396 | 31559 | 17522 | 12082 | 9232 | 9902
Sl No | Available Capacity (NPK) | Total Available Hour | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01
1.1 | KHURDA-WELDING-SMI | 19367.9169 | 1591.8836 | 1644.9464 | 1644.9464 | 1591.8836 | 1644.9464 | 1591.8836 | 1644.9464 | 1644.9464 | 1485.758 | 1644.9464 | 1591.8836 | 1644.9464
1.2 | KHURDA-WELDING-LS | 261466.8785 | 21490.4284 | 22206.776 | 22206.776 | 21490.4284 | 22206.776 | 21490.4284 | 22206.776 | 22206.776 | 20057.7331 | 22206.776 | 21490.4284 | 22206.776
1.3 | KHURDA-WELDING-JC | 180767.2246 | 14857.5801 | 15352.8328 | 15352.8328 | 14857.5801 | 15352.8328 | 14857.5801 | 15352.8328 | 15352.8328 | 13867.0748 | 15352.8328 | 14857.5801 | 15352.8328
1.1-1.3 | KHURDA-WELDING (SMI+LS+JC) | 461602.02 | 37939.8921 | 39204.5551 | 39204.5551 | 37939.8921 | 39204.5551 | 37939.8921 | 39204.5551 | 39204.5551 | 35410.5659 | 39204.5551 | 37939.8921 | 39204.5551
1.4 | MANCHESWAR-WELDING-JC | 140252.0968 | 11527.5696 | 11911.8219 | 11911.8219 | 11527.5696 | 11911.8219 | 11527.5696 | 11911.8219 | 11911.8219 | 10759.065 | 11911.8219 | 11527.5696 | 11911.8219
1.5 | MANCHESWAR-WELDING-LS | 6233.4265 | 512.3364 | 529.4143 | 529.4143 | 512.3364 | 529.4143 | 512.3364 | 529.4143 | 529.4143 | 478.1807 | 529.4143 | 512.3364 | 529.4143
1.6 | MANCHESWAR-WELDING-SMI | 1558.3566 | 128.0841 | 132.3536 | 132.3536 | 128.0841 | 132.3536 | 128.0841 | 132.3536 | 132.3536 | 119.5452 | 132.3536 | 128.0841 | 132.3536
1.7 | MANCHESWAR-WELDING (SMI+LS+JC) | 148043.88 | 12167.9901 | 12573.5898 | 12573.5898 | 12167.9901 | 12573.5898 | 12167.9901 | 12573.5898 | 12573.5898 | 11356.7908 | 12573.5898 | 12167.9901 | 12573.5898
1 | K & M - WELDING (TOTAL) | 609645.9 | 50107.8822 | 51778.1449 | 51778.1449 | 50107.8822 | 51778.1449 | 50107.8822 | 51778.1449 | 51778.1449 | 46767.3567 | 51778.1449 | 50107.8822 | 51778.1449
2 | TOTAL MACHINE SHOP | 106306.0285 | 8737.4818 | 9028.7312 | 9028.7312 | 8737.4818 | 9028.7312 | 8737.4818 | 9028.7312 | 9028.7312 | 8154.983 | 9028.7312 | 8737.4818 | 9028.7312
3.1 | ASSEMBLY-SMI | 16496.625 | 1355.887 | 1401.0832 | 1401.0832 | 1355.887 | 1401.0832 | 1355.887 | 1401.0832 | 1401.0832 | 1265.4945 | 1401.0832 | 1355.887 | 1401.0832
3.2 | ASSEMBLY-LS | 32993.25 | 2711.774 | 2802.1664 | 2802.1664 | 2711.774 | 2802.1664 | 2711.774 | 2802.1664 | 2802.1664 | 2530.989 | 2802.1664 | 2711.774 | 2802.1664
3.3 | ASSEMBLY-JS | 16496.625 | 1355.887 | 1401.0832 | 1401.0832 | 1355.887 | 1401.0832 | 1355.887 | 1401.0832 | 1401.0832 | 1265.4945 | 1401.0832 | 1355.887 | 1401.0832
3 | ASSEMBLY-MFG | 65986.5 | 5423.5479 | 5604.3329 | 5604.3329 | 5423.5479 | 5604.3329 | 5423.5479 | 5604.3329 | 5604.3329 | 5061.9781 | 5604.3329 | 5423.5479 | 5604.3329
4 | ROLL REFURBISHMENT | 27553.4748 | 2264.6692 | 2340.1581 | 2340.1581 | 2264.6692 | 2340.1581 | 2264.6692 | 2340.1581 | 2340.1581 | 2113.6912 | 2340.1581 | 2264.6692 | 2340.1581
5 | PLATING | 29700.06 | 2441.1008 | 2522.4708 | 2522.4708 | 2441.1008 | 2522.4708 | 2441.1008 | 2522.4708 | 2522.4708 | 2278.3608 | 2522.4708 | 2441.1008 | 2522.4708
| TOTAL MANUFACTRING | 839191.9633 | 68974.6819 | 71273.838 | 71273.838 | 68974.6819 | 71273.838 | 68974.6819 | 71273.838 | 71273.838 | 64376.3698 | 71273.838 | 68974.6819 | 71273.838
|  |  | 96.9% | 90.16% | 89.37% | 85.79% | 83.71% | 80.03% | 52.47% | 44.28% | 27.22% | 16.95% | 13.38% | 13.89%
TOTAL GROUP COMPANY HOURS |  | 129163 | 15265.5 | 15502.5 | 15590.5 | 16853.5 | 21309.5 | 22240.5 | 10726 | 10170 | 1345 | 160 | 0 | 0
|  |  | 15.2655 | 15.5025 | 15.5905 | 16.8535 | 21.3095 | 22.2405 | 10.726 | 10.17 | 1.345 | 0.16 | 0 | 0
TOTAL CONTRACT MANUFACTURING HOURS |  | 41593 | 6975.5 | 7516.5 | 4789 | 3879 | 4028 | 2985 | 2910 | 2910 | 2800 | 2800 | 0 | 0
|  |  | 6.9755 | 7.5165 | 4.789 | 3.879 | 4.028 | 2.985 | 2.91 | 2.91 | 2.8 | 2.8 | 0 | 0
|  | Total | 22.241 | 23.019 | 20.3795 | 20.7325 | 25.3375 | 25.2255 | 13.636 | 13.08 | 4.145 | 2.96 | 0 | 0

## SCB ACTUAL
Planned | 2026-01-06 | 2026-02-07 | 2026-03-11 | 2026-04-12 | 2026-05-14 | 2026-06-15 | 2026-07-17 | 2026-08-18 | 2026-09-19 | 2026-10-21 | 2026-11-22 | 2026-12-24 | Planned Hours Apr'26-Dec'26
WELDING | 51351.295 | 47293 | 51849 | 52535 | 52485 | 49831.25 | 49026.75 | 47313.75 | 44617.75 | 44183.5 | 41776.5 | 24975 | 301724.5
MACHINING | 7519.22 | 8153 | 9028 | 8947 | 9129 | 8475 | 6792.5 | 8144 | 6540 | 7635 | 6550 | 5756 | 49892.5
ASSEMBLY | 4945.01 | 5159 | 5700 | 5686 | 5630 | 5428 | 5543 | 5538 | 5614 | 5542 | 4785 | 4765 | 37215
ROLL REFURBISHMENT | 2765.02 | 2200 | 1600 | 1600 | 1500 | 1800 | 1600 | 1500 | 1400 | 1300 | 1200 | 1100 | 9900
PLATING | 4021 | 2522 | 2200 | 1300 | 1300 | 1300 | 1300 | 1200 | 1000 | 1000 | 890 | 800 | 7490
TOTAL | 70601.545 | 65327 | 70377 | 70068 | 70044 | 66834.25 | 64262.25 | 63695.75 | 59171.75 | 59660.5 | 55201.5 | 37396 | 406222
NPK Capacity | 2026-01-06 | 2026-02-07 | 2026-03-11 | 2026-04-12 | 2026-05-14 | 2026-06-15 | 2026-07-17 | 2026-08-18 | 2026-09-19 | 2026-10-21 | 2026-11-22 | 2026-12-24 | Planned Hours Apr'26-Dec'26
WELDING | 51778.1449 | 46767 | 51778.1449 | 50107.8822 | 51778.1449 | 50107.8822 | 51778.1449 | 51778.1449 | 50107.8822 | 51778.1449 | 50107.8822 | 51778.1449 | 357436.2263
MACHINING | 9028.7312 | 8155 | 9028.7312 | 8737.4818 | 9028.7312 | 8737.4818 | 9028.7312 | 9028.7312 | 8737.4818 | 9028.7312 | 8737.4818 | 9028.7312 | 62327.3701
ASSEMBLY | 5604.3329 | 5062 | 5604.3329 | 5423.5479 | 5604.3329 | 5423.5479 | 5604.3329 | 5604.3329 | 5423.5479 | 5604.3329 | 5423.5479 | 5604.3329 | 38687.9753
ROLL REFURBISHMENT | 2340.1581 | 2340 | 2340.1581 | 2340.1581 | 2264.6692 | 2264.6692 | 2340.1581 | 2340.1581 | 2264.6692 | 2340.1581 | 2264.6692 | 2340.1581 | 16154.64
PLATING | 2522.4708 | 2522 | 2522.4708 | 2522.4708 | 2441.1008 | 2441.1008 | 2522.4708 | 2522.4708 | 2441.1008 | 2522.4708 | 2441.1008 | 2522.4708 | 17413.1859
TOTAL | 71273.838 | 64846 | 71273.838 | 69131.5409 | 71116.979 | 68974.6819 | 71273.838 | 71273.838 | 68974.6819 | 71273.838 | 68974.6819 | 71273.838 | 492019.3977
Planned Hours | 2026-01-06 | 2026-02-07 | 2026-03-11 | 2026-04-12 | 2026-05-14 | 2026-06-15 | 2026-07-17 | 2026-08-18 | 2026-09-19 | 2026-10-21 | 2026-11-22 | 2026-12-24 | Planned Hours Apr'26-Dec'26
WELDING | 51.3513 | 47.293 | 51.849 | 52.535 | 52.485 | 49.8312 | 49.0267 | 47.3137 | 44.6178 | 44.1835 | 41.7765 | 24.975 | 301.7245
MACHINING | 7.5192 | 8.153 | 9.028 | 8.947 | 9.129 | 8.475 | 6.7925 | 8.144 | 6.54 | 7.635 | 6.55 | 5.756 | 49.8925
ASSEMBLY | 4.945 | 5.159 | 5.7 | 5.686 | 5.63 | 5.428 | 5.543 | 5.538 | 5.614 | 5.542 | 4.785 | 4.765 | 37.215
ROLL REFURBISHMENT | 2.765 | 2.2 | 1.6 | 1.6 | 1.5 | 1.8 | 1.6 | 1.5 | 1.4 | 1.3 | 1.2 | 1.1 | 9.9
PLATING | 4.021 | 2.522 | 2.2 | 1.3 | 1.3 | 1.3 | 1.3 | 1.2 | 1 | 1 | 0.89 | 0.8 | 7.49
LOI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 11 | 27 | 44
GROUP COMPANY | 10.9 | 4.1 | 5.4 | 10.646 | 8.49 | 15.2655 | 15.5025 | 15.5905 | 16.8535 | 21.3095 | 22.2405 | 10.726 | 117.488
CONTRACT MFG. | 7.1396 | 13.3 | 11.57 | 11.57 | 11.779 | 6.9755 | 7.5165 | 4.789 | 3.879 | 4.028 | 2.985 | 2.91 | 33.083
PLANNED HOURS | 70.6015 | 65.327 | 70.377 | 70.068 | 70.044 | 66.8342 | 64.2622 | 63.6958 | 59.1717 | 59.6605 | 55.2015 | 37.396 | 406.222
NPK | 2026-01-06 | 2026-02-07 | 2026-03-11 | 2026-04-12 | 2026-05-14 | 2026-06-15 | 2026-07-17 | 2026-08-18 | 2026-09-19 | 2026-10-21 | 2026-11-22 | 2026-12-24 | Planned Hours Apr'26-Dec'26
WELDING | 51.7781 | 46.767 | 51.7781 | 50.1079 | 51.7781 | 50.1079 | 51.7781 | 51.7781 | 50.1079 | 51.7781 | 50.1079 | 51.7781 | 357.4362
MACHINING | 9.0287 | 8.155 | 9.0287 | 8.7375 | 9.0287 | 8.7375 | 9.0287 | 9.0287 | 8.7375 | 9.0287 | 8.7375 | 9.0287 | 62.3274
ASSEMBLY | 5.6043 | 5.062 | 5.6043 | 5.4235 | 5.6043 | 5.4235 | 5.6043 | 5.6043 | 5.4235 | 5.6043 | 5.4235 | 5.6043 | 38.688
ROLL REFURBISHMENT | 2.3402 | 2.34 | 2.3402 | 2.3402 | 2.2647 | 2.2647 | 2.3402 | 2.3402 | 2.2647 | 2.3402 | 2.2647 | 2.3402 | 16.1546
PLATING | 2.5225 | 2.522 | 2.5225 | 2.5225 | 2.4411 | 2.4411 | 2.5225 | 2.5225 | 2.4411 | 2.5225 | 2.4411 | 2.5225 | 17.4132
PLANNED HOURS | 71.2738 | 64.846 | 71.2738 | 69.1315 | 71.117 | 68.9747 | 71.2738 | 71.2738 | 68.9747 | 71.2738 | 68.9747 | 71.2738 | 492.0194
UTILIZATION (%) | 99.06% | 100.7% | 98.74% | 101.4% | 98.49% | 96.9% | 90.16% | 89.37% | 85.79% | 83.71% | 80.03% | 52.47% | 82.56%
NPK | 2026-01-06: 492.0194; 2026-02-07: Planned Hour; 2026-03-11: NPK
Planned Hours | 2026-01-06: 40622%; 2026-02-07: 89%; 2026-03-11: 11%

## SCB PLAN
Planned | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | Planned Hours Jun'26-May'27
WELDING | 49831.25 | 49026.75 | 47313.75 | 44617.75 | 44183.5 | 41776.5 | 24975 | 20989 | 9300 | 6550 | 4050 | 4050 | 346663.5
MACHINING | 8475 | 6792.5 | 8144 | 6540 | 7635 | 6550 | 5756 | 4610 | 3982 | 2236 | 3582 | 4282 | 68584.5
ASSEMBLY | 5428 | 5543 | 5538 | 5614 | 5542 | 4785 | 4765 | 4160 | 2540 | 1620 | 100 | 100 | 45735
ROLL REFURBISHMENT | 1800 | 1600 | 1500 | 1400 | 1300 | 1200 | 1100 | 1100 | 1100 | 1176 | 1000 | 1000 | 15276
PLATING | 1300 | 1300 | 1200 | 1000 | 1000 | 890 | 800 | 700 | 600 | 500 | 500 | 470 | 10260
TOTAL | 66834.25 | 64262.25 | 63695.75 | 59171.75 | 59660.5 | 55201.5 | 37396 | 31559 | 17522 | 12082 | 9232 | 9902 | 486519
NPK Capacity | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | Planned Hours Jun'26-May'27
WELDING | 50107.8822 | 51778.1449 | 51778.1449 | 50107.8822 | 51778.1449 | 50107.8822 | 51778.1449 | 51778.1449 | 46767.3567 | 51778.1449 | 50107.8822 | 51778.1449 | 609645.9
MACHINING | 9028.7312 | 8154.983 | 9028.7312 | 8737.4818 | 9028.7312 | 8737.4818 | 9028.7312 | 9028.7312 | 8737.4818 | 9028.7312 | 8737.4818 | 9028.7312 | 106306.0285
ASSEMBLY | 5423.5479 | 5604.3329 | 5604.3329 | 5423.5479 | 5604.3329 | 5423.5479 | 5604.3329 | 5604.3329 | 5061.9781 | 5604.3329 | 5423.5479 | 5604.3329 | 65986.5
ROLL REFURBISHMENT | 2264.6692 | 2340.1581 | 2340.1581 | 2264.6692 | 2340.1581 | 2264.6692 | 2340.1581 | 2340.1581 | 2113.6912 | 2340.1581 | 2264.6692 | 2340.1581 | 27553.4748
PLATING | 2441.1008 | 2522.4708 | 2522.4708 | 2441.1008 | 2522.4708 | 2441.1008 | 2522.4708 | 2522.4708 | 2278.3608 | 2522.4708 | 2441.1008 | 2522.4708 | 29700.06
TOTAL | 69265.9313 | 70400.0898 | 71273.838 | 68974.6819 | 71273.838 | 68974.6819 | 71273.838 | 71273.838 | 64958.8686 | 71273.838 | 68974.6819 | 71273.838 | 839191.9633
Planned Hours | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | Planned Hours Jun'26-May'27
WELDING | 49.8312 | 49.0267 | 47.3137 | 44.6178 | 44.1835 | 41.7765 | 24.975 | 20.989 | 9.3 | 6.55 | 4.05 | 4.05 | 346.6635
MACHINING | 8.475 | 6.7925 | 8.144 | 6.54 | 7.635 | 6.55 | 5.756 | 4.61 | 3.982 | 2.236 | 3.582 | 4.282 | 68.5845
ASSEMBLY | 5.428 | 5.543 | 5.538 | 5.614 | 5.542 | 4.785 | 4.765 | 4.16 | 2.54 | 1.62 | 0.1 | 0.1 | 45.735
ROLL REFURBISHMENT | 1.8 | 1.6 | 1.5 | 1.4 | 1.3 | 1.2 | 1.1 | 1.1 | 1.1 | 1.176 | 1 | 1 | 15.276
PLATING | 1.3 | 1.3 | 1.2 | 1 | 1 | 0.89 | 0.8 | 0.7 | 0.6 | 0.5 | 0.5 | 0.47 | 10.26
LOI | 0 | 0 | 0 | 0 | 6 | 11 | 27 | 31 | 35 | 35 | 35 | 35 | 215
GROUP COMPANY | 15.2655 | 15.5025 | 15.5905 | 16.8535 | 21.3095 | 22.2405 | 10.726 | 10.17 | 1.345 | 0.16 | 0 | 0 | 129.163
CONTRACT MFG. | 6.9755 | 7.5165 | 4.789 | 3.879 | 4.028 | 2.985 | 2.91 | 2.91 | 2.8 | 2.8 | 0 | 0 | 41.593
PLANNED HOURS | 66.8342 | 64.2622 | 63.6958 | 59.1717 | 59.6605 | 55.2015 | 37.396 | 31.559 | 17.522 | 12.082 | 9.232 | 9.902 | 486.519
NPK | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | Planned Hours Jun'26-May'27
WELDING | 50.1079 | 51.7781 | 51.7781 | 50.1079 | 51.7781 | 50.1079 | 51.7781 | 51.7781 | 46.7674 | 51.7781 | 50.1079 | 51.7781 | 609.6459
MACHINING | 9.0287 | 8.155 | 9.0287 | 8.7375 | 9.0287 | 8.7375 | 9.0287 | 9.0287 | 8.7375 | 9.0287 | 8.7375 | 9.0287 | 106.306
ASSEMBLY | 5.4235 | 5.6043 | 5.6043 | 5.4235 | 5.6043 | 5.4235 | 5.6043 | 5.6043 | 5.062 | 5.6043 | 5.4235 | 5.6043 | 65.9865
ROLL REFURBISHMENT | 2.2647 | 2.3402 | 2.3402 | 2.2647 | 2.3402 | 2.2647 | 2.3402 | 2.3402 | 2.1137 | 2.3402 | 2.2647 | 2.3402 | 27.5535
PLATING | 2.4411 | 2.5225 | 2.5225 | 2.4411 | 2.5225 | 2.4411 | 2.5225 | 2.5225 | 2.2784 | 2.5225 | 2.4411 | 2.5225 | 29.7001
PLANNED HOURS | 69.2659 | 70.4001 | 71.2738 | 68.9747 | 71.2738 | 68.9747 | 71.2738 | 71.2738 | 64.9589 | 71.2738 | 68.9747 | 71.2738 | 839.192
UTILIZATION (%) | 96.49% | 91.28% | 89.37% | 85.79% | 83.71% | 80.03% | 52.47% | 44.28% | 26.97% | 16.95% | 13.38% | 13.89% | 57.97%
NPK | 2026-06-01: NPK
Planned Hours | 2026-06-01: 11%

## TS
WORK centre | Product Group | Month | capacity | Planned | Inactual job availability
MAATASLY | Assembly/ Testing | 2026-06-01 | 5537 | 700 | 700
|  | 2026-07-01 | 5537 | 700 | 700
|  | 2026-08-01 | 5537 | 700 | 700
|  | 2026-09-01 | 5537 | 1500 | Job yet to receive | 1566
|  | 2026-10-01 | 5537 | 1500 |  | 1566
|  | 2026-11-01 | 5537 | 1500 |  | 1566
|  | 2026-12-01 | 5537 | 1500 |  | 1566
|  | 2027-01-27 | 5537 | 1500 |  | 1566
|  | 2027-02-01 | 5537 | 1500 |  | 1566
|  | 2027-03-27 | 5537 | 1500 |  | 1566
|  | 2027-04-01 | 5537 | 1500 |  | 1566
|  | 2026-05-01 | 5537 | 1500 |  | 1566
SKCCCYRE | Hydraulic Test Stand | 2026-06-01 | 66 | 20 | 20
|  | 2026-07-01 | 66 | 20 | 20
|  | 2026-08-01 | 66 | 20 | 20
|  | 2026-09-01 | 66 | 66 | Job yet to receive
|  | 2026-10-01 | 66 | 66
|  | 2026-11-01 | 66 | 66
|  | 2026-12-01 | 66 | 66
|  | 2027-01-27 | 66 | 66
|  | 2027-02-01 | 66 | 66
|  | 2027-03-27 | 66 | 66
|  | 2027-04-01 | 66 | 66
|  | 2026-05-01 | 66 | 66
CC |  | Total | 67236 | 16254
SKRRASDI | Assembly / Disassembly | 2026-06-01 | 1153 | 900 | 900 | 1848
|  | 2026-07-01 | 1153 | 900 | 900 | 1848
|  | 2026-08-01 | 1153 | 900 | 900 | 1848
|  | 2026-09-01 | 1153 | 600 | 900 | 1548
|  | 2026-10-01 | 1153 | 600 | 900 | 1548
|  | 2026-11-01 | 1153 | 600 | Job yet to receive | 948
|  | 2026-12-01 | 1153 | 600 |  | 948
|  | 2027-01-27 | 1153 | 600 |  | 948
|  | 2027-02-01 | 1153 | 600 |  | 948
|  | 2027-03-27 | 1153 | 600 |  | 948
|  | 2027-04-01 | 1153 | 600 |  | 948
|  | 2026-05-01 | 1153 | 600 |  | 948
SKRRL500 | 500 mm - 2 Head Roll Welding Lathe | 2026-06-01 | 350 | 350
|  | 2026-07-01 | 350 | 350
|  | 2026-08-01 | 350 | 350
|  | 2026-09-01 | 350 | 350
|  | 2026-10-01 | 350 | 350
|  | 2026-11-01 | 350 | 350
|  | 2026-12-01 | 350 | 350
|  | 2027-01-27 | 350 | 350
|  | 2027-02-01 | 350 | 350
|  | 2027-03-27 | 350 | 350
|  | 2027-04-01 | 350 | 350
|  | 2026-05-01 | 350 | 350
SKRRL11M | 1100 mm - 2 Head Roll Welding Lathe | 2026-06-01 | 350 | 350
|  | 2026-07-01 | 350 | 350
|  | 2026-08-01 | 350 | 350
|  | 2026-09-01 | 350 | 350
|  | 2026-10-01 | 350 | 350
|  | 2026-11-01 | 350 | 350
|  | 2026-12-01 | 350 | 350
|  | 2027-01-27 | 350 | 350
|  | 2027-02-01 | 350 | 350
|  | 2027-03-27 | 350 | 350
|  | 2027-04-01 | 350 | 350
|  | 2026-05-01 | 350 | 350
SKRRFURN | Furnace | 2026-06-01 | 248 | 248
|  | 2026-07-01 | 248 | 248
|  | 2026-08-01 | 248 | 248
|  | 2026-09-01 | 248 | 248
|  | 2026-10-01 | 248 | 248
|  | 2026-11-01 | 248 | 248
|  | 2026-12-01 | 248 | 248
|  | 2027-01-27 | 248 | 248
|  | 2027-02-01 | 248 | 248
|  | 2027-03-27 | 248 | 248
|  | 2027-04-01 | 248 | 248
|  | 2026-05-01 | 248 | 248
RR |  | Total | 25212 | 19476
SKPLASDI | Plating / HVOF Labour Hours | 2026-06-01 | 217 | 200 | 200 | 2880
|  | 2026-07-01 | 217 | 200 | 200 | 2880
|  | 2026-08-01 | 217 | 200 | 200 | 2880
|  | 2026-09-01 | 217 | 150 | Job yet to receive | 1620 | 850
|  | 2026-10-01 | 217 | 150 |  |  | 1650
|  | 2026-11-01 | 217 | 150 |  |  | 1650
|  | 2026-12-01 | 217 | 150 |  |  | 1650
|  | 2027-01-27 | 217 | 150 |  |  | 1650
|  | 2027-02-01 | 217 | 150 |  |  | 1650
|  | 2027-03-27 | 217 | 150 |  |  | 1650
|  | 2027-04-01 | 217 | 150 |  |  | 1650
|  | 2026-05-01 | 217 | 150 |  |  | 1600
SKPLBOXP | Box Plating | 2026-06-01 | 1612 | 1500 | 1500
|  | 2026-07-01 | 1612 | 1500 | 1500
|  | 2026-08-01 | 1612 | 1500 | 1500
|  | 2026-09-01 | 1612 | 1500 | 1500
|  | 2026-10-01 | 1612 | 700 | Job yet to receive
|  | 2026-11-01 | 1612 | 700
|  | 2026-12-01 | 1612 | 700
|  | 2027-01-27 | 1612 | 700
|  | 2027-02-01 | 1612 | 700
|  | 2027-03-27 | 1612 | 700
|  | 2027-04-01 | 1612 | 700
|  | 2026-05-01 | 1612 | 700
SKPLDIPP | Dip Plating | 2026-06-01 | 780 | 780 | 780
|  | 2026-07-01 | 780 | 780 | 780
|  | 2026-08-01 | 780 | 780 | 780
|  | 2026-09-01 | 780 | 500 | Job yet to receive
|  | 2026-10-01 | 780 | 500
|  | 2026-11-01 | 780 | 500
|  | 2026-12-01 | 780 | 500
|  | 2027-01-27 | 780 | 500
|  | 2027-02-01 | 780 | 500
|  | 2027-03-27 | 780 | 500
|  | 2027-04-01 | 780 | 500
|  | 2026-05-01 | 780 | 500
SKPLHVOF | HVOF Machine | 2026-06-01 | 280 | 280 | 280
|  | 2026-07-01 | 280 | 280 | 280
|  | 2026-08-01 | 280 | 280 | 280
|  | 2026-09-01 | 280 | 200 | Job yet to receive
|  | 2026-10-01 | 280 | 200
|  | 2026-11-01 | 280 | 200
|  | 2026-12-01 | 280 | 200
|  | 2027-01-27 | 280 | 200
|  | 2027-02-01 | 280 | 200
|  | 2027-03-27 | 280 | 200
|  | 2027-04-01 | 280 | 200
|  | 2026-05-01 | 280 | 150
SKPLBLST | Grit Blasting Machine | 2026-06-01 | 150 | 120 | 120
|  | 2026-07-01 | 150 | 120 | 120
|  | 2026-08-01 | 150 | 120 | 120
|  | 2026-09-01 | 150 | 120 | 120
|  | 2026-10-01 | 150 | 100 | Job yet to receive
|  | 2026-11-01 | 150 | 100
|  | 2026-12-01 | 150 | 100
|  | 2027-01-27 | 150 | 100
|  | 2027-02-01 | 150 | 100
|  | 2027-03-27 | 150 | 100
|  | 2027-04-01 | 150 | 100
|  | 2026-05-01 | 150 | 100
PL |  | Total | 36468 | 24260 |  |  |  | MILL | LATHE
SKMSCN5A | 5 Axis CNC Milling Machine | 2026-06-01 | 540 | 540 |  |  | 4472 | 1940 | 2532
|  | 2026-07-01 | 540 | 540 |  |  | 4472 | 1940 | 2532
|  | 2026-08-01 | 540 | 540 |  |  | 4472 | 1940 | 2532
|  | 2026-09-01 | 540 | 540 |  |  | 4072 | 1540 | 2532
|  | 2026-10-01 | 540 | 300 |  |  | 3232 | 1000 | 2232
|  | 2026-11-01 | 540 | 300 |  |  | 2982 | 750 | 2232
|  | 2026-12-01 | 540 | 300 |  |  | 2832 | 600 | 2232
|  | 2027-01-27 | 540 | 300 |  |  | 2832 | 600 | 2232
|  | 2027-02-01 | 540 | 300 |  |  | 2832 | 600 | 2232
|  | 2027-03-27 | 540 | 300 |  |  | 2832 | 600 | 2232
|  | 2027-04-01 | 540 | 300 |  |  | 2832 | 600 | 2232
|  | 2026-05-01 | 540 | 300 |  |  | 2832 | 600 | 2232
SKMSCN3A | 3 Axis CNC Milling Machine | 2026-06-01 | 420 | 400
|  | 2026-07-01 | 420 | 400
|  | 2026-08-01 | 420 | 400
|  | 2026-09-01 | 420 | 400
|  | 2026-10-01 | 420 | 400
|  | 2026-11-01 | 420 | 150
|  | 2026-12-01 | 420 | 150
|  | 2027-01-27 | 420 | 150
|  | 2027-02-01 | 420 | 150
|  | 2027-03-27 | 420 | 150
|  | 2027-04-01 | 420 | 150
|  | 2026-05-01 | 420 | 150
SKMSLTH5 | 5 Meter CNC Lathe | 2026-06-01 | 1116 | 1116
|  | 2026-07-01 | 1116 | 1116
|  | 2026-08-01 | 1116 | 1116
|  | 2026-09-01 | 1116 | 1116
|  | 2026-10-01 | 1116 | 1116
|  | 2026-11-01 | 1116 | 1116
|  | 2026-12-01 | 1116 | 1116
|  | 2027-01-27 | 1116 | 1116
|  | 2027-02-01 | 1116 | 1116
|  | 2027-03-27 | 1116 | 1116
|  | 2027-04-01 | 1116 | 1116
|  | 2026-05-01 | 1116 | 1116
SKMSLTH3 | 3 Meter CNC Lathe | 2026-06-01 | 1116 | 1116
|  | 2026-07-01 | 1116 | 1116
|  | 2026-08-01 | 1116 | 1116
|  | 2026-09-01 | 1116 | 1116
|  | 2026-10-01 | 1116 | 1116
|  | 2026-11-01 | 1116 | 1116
|  | 2026-12-01 | 1116 | 1116
|  | 2027-01-27 | 1116 | 1116
|  | 2027-02-01 | 1116 | 1116
|  | 2027-03-27 | 1116 | 1116
|  | 2027-04-01 | 1116 | 1116
|  | 2026-05-01 | 1116 | 1116
MMMCSKHB | SKODA Machine | 2026-06-01 | 600 | 600
|  | 2026-07-01 | 600 | 600
|  | 2026-08-01 | 600 | 600
|  | 2026-09-01 | 600 | 600
|  | 2026-10-01 | 600 | 300
|  | 2026-11-01 | 600 | 300
|  | 2026-12-01 | 600 | 150
|  | 2027-01-27 | 600 | 150
|  | 2027-02-01 | 600 | 150
|  | 2027-03-27 | 600 | 150
|  | 2027-04-01 | 600 | 150
|  | 2026-05-01 | 600 | 150
MMMCCNC8 | 8 Meter CNC Lathe | 2026-06-01 | 465 | 300 | 300
|  | 2026-07-01 | 465 | 300 | 300
|  | 2026-08-01 | 465 | 300 | 300
|  | 2026-09-01 | 465 | 300 | 300 |  |  |  | 500
|  | 2026-10-01 | 465 | 300 | Job yet to receive |  | 800 |  | 800
|  | 2026-11-01 | 465 | 300 |  |  | 800 |  | 800
|  | 2026-12-01 | 465 | 300 |  |  | 800 |  | 800
|  | 2027-01-27 | 465 | 300 |  |  | 800 |  | 800
|  | 2027-02-01 | 465 | 300 |  |  | 800 |  | 800
|  | 2027-03-27 | 465 | 300 |  |  | 800 |  | 800
|  | 2027-04-01 | 465 | 300 |  |  | 800 |  | 800
|  | 2026-05-01 | 465 | 300 |  |  | 800 |  | 800
MMMCIBPM | CNC Plano Miller | 2026-06-01 | 600 | 400 | 400
|  | 2026-07-01 | 600 | 400 | 400
|  | 2026-08-01 | 600 | 400 | 400
|  | 2026-09-01 | 600 | 500 | Job yet to receive
|  | 2026-10-01 | 600 | 500
|  | 2026-11-01 | 600 | 500
|  | 2026-12-01 | 600 | 500
|  | 2027-01-27 | 600 | 500
|  | 2027-02-01 | 600 | 500
|  | 2027-03-27 | 600 | 500
|  | 2027-04-01 | 600 | 500
|  | 2026-05-01 | 600 | 500
MS |  | Total | 58284 | 47594

## NPK
Sl No | Available Capacity (NPK)-2026 | Total Available Hour | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01
1.1 | KHURDA-WELDING-SMI | 19367.9169 | 1644.9464 | 1485.758 | 1644.9464 | 1591.8836 | 1644.9464 | 1591.8836 | 1644.9464 | 1644.9464 | 1591.8836 | 1644.9464 | 1591.8836 | 1644.9464
1.2 | KHURDA-WELDING-LS | 261466.8785 | 22206.776 | 20057.7331 | 22206.776 | 21490.4284 | 22206.776 | 21490.4284 | 22206.776 | 22206.776 | 21490.4284 | 22206.776 | 21490.4284 | 22206.776
1.3 | KHURDA-WELDING-JC | 180767.2246 | 15352.8328 | 13867.0748 | 15352.8328 | 14857.5801 | 15352.8328 | 14857.5801 | 15352.8328 | 15352.8328 | 14857.5801 | 15352.8328 | 14857.5801 | 15352.8328
1.1-1.3 | KHURDA-WELDING (SMI+LS+JC) | 461602.02 | 39204.5551 | 35410.5659 | 39204.5551 | 37939.8921 | 39204.5551 | 37939.8921 | 39204.5551 | 39204.5551 | 37939.8921 | 39204.5551 | 37939.8921 | 39204.5551
1.4 | MANCHESWAR-WELDING-JC | 140252.0968 | 11911.8219 | 10759.065 | 11911.8219 | 11527.5696 | 11911.8219 | 11527.5696 | 11911.8219 | 11911.8219 | 11527.5696 | 11911.8219 | 11527.5696 | 11911.8219
1.5 | MANCHESWAR-WELDING-LS | 6233.4265 | 529.4143 | 478.1807 | 529.4143 | 512.3364 | 529.4143 | 512.3364 | 529.4143 | 529.4143 | 512.3364 | 529.4143 | 512.3364 | 529.4143
1.6 | MANCHESWAR-WELDING-SMI | 1558.3566 | 132.3536 | 119.5452 | 132.3536 | 128.0841 | 132.3536 | 128.0841 | 132.3536 | 132.3536 | 128.0841 | 132.3536 | 128.0841 | 132.3536
1 | K & M - WELDING (TOTAL) | 609645.9 | 51778.1449 | 46767.3567 | 51778.1449 | 50107.8822 | 51778.1449 | 50107.8822 | 51778.1449 | 51778.1449 | 50107.8822 | 51778.1449 | 50107.8822 | 51778.1449
2 | TOTAL MACHINE SHOP | 106306.0285 | 9028.7312 | 8154.983 | 9028.7312 | 8737.4818 | 9028.7312 | 8737.4818 | 9028.7312 | 9028.7312 | 8737.4818 | 9028.7312 | 8737.4818 | 9028.7312
3.1 | ASSEMBLY-SMI | 16496.625 | 1401.0832 | 1265.4945 | 1401.0832 | 1355.887 | 1401.0832 | 1355.887 | 1401.0832 | 1401.0832 | 1355.887 | 1401.0832 | 1355.887 | 1401.0832
3.2 | ASSEMBLY-LS | 32993.25 | 2802.1664 | 2530.989 | 2802.1664 | 2711.774 | 2802.1664 | 2711.774 | 2802.1664 | 2802.1664 | 2711.774 | 2802.1664 | 2711.774 | 2802.1664
3.3 | ASSEMBLY-JS | 16496.625 | 1401.0832 | 1265.4945 | 1401.0832 | 1355.887 | 1401.0832 | 1355.887 | 1401.0832 | 1401.0832 | 1355.887 | 1401.0832 | 1355.887 | 1401.0832
3 | ASSEMBLY-MFG | 65986.5 | 5604.3329 | 5061.9781 | 5604.3329 | 5423.5479 | 5604.3329 | 5423.5479 | 5604.3329 | 5604.3329 | 5423.5479 | 5604.3329 | 5423.5479 | 5604.3329
4 | ROLL REFURBISHMENT | 27553.4748 | 2340.1581 | 2113.6912 | 2340.1581 | 2264.6692 | 2340.1581 | 2264.6692 | 2340.1581 | 2340.1581 | 2264.6692 | 2340.1581 | 2264.6692 | 2340.1581
5 | PLATING | 29700.06 | 2522.4708 | 2278.3608 | 2522.4708 | 2441.1008 | 2522.4708 | 2441.1008 | 2522.4708 | 2522.4708 | 2441.1008 | 2522.4708 | 2441.1008 | 2522.4708
| TOTAL MANUFACTRING | 839191.9633 | 71273.838 | 64376.3698 | 71273.838 | 68974.6819 | 71273.838 | 68974.6819 | 71273.838 | 71273.838 | 68974.6819 | 71273.838 | 68974.6819 | 71273.838

## Welding
Row Labels | Sum of Jun/26 | Sum of Jul/26 | Sum of Aug/26 | Sum of Sep/26 | Sum of Oct/26 | Sum of Nov/26 | Sum of Dec/26 | Sum of Jan/27 | Sum of Feb/27 | Sum of Mar/27 | Sum of Apr/27 | Sum of May/27
Contract | 4532.5 | 5139.5 | 4322 | 3569 | 3568 | 2500 | 2500 | 2500 | 2500 | 2500
Group | 14938.5 | 15175.5 | 14938.5 | 16142.5 | 20441.5 | 21440.5 | 9884 | 9385 | 450
OTH | 30360.25 | 28711.75 | 28053.25 | 24906.25 | 20174 | 17836 | 12591 | 9104 | 6350 | 4050 | 4050 | 4050
(blank) | 49831.25 | 49026.75 | 47313.75 | 44617.75 | 44183.5 | 41776.5 | 24975 | 20989 | 9300 | 6550 | 4050 | 4050
Grand Total | 99662.5 | 98053.5 | 94627.5 | 89235.5 | 88367 | 83553 | 49950 | 41978 | 18600 | 13100 | 8100 | 8100

## Machining
Milling Machining
Row Labels | Sum of Jun-26 | Sum of Jul-26 | Sum of Aug-26 | Sum of Sep-26 | Sum of Oct-26 | Sum of Nov-26 | Sum of Dec-26 | Sum of Jan-27 | Sum of Feb-27 | Sum of Mar-27 | Sum of Apr-27 | Sum of May-27
Contract | 731 | 610 | 310 | 110 | 10 | 85 | 10 | 10
Group | 327 | 327 | 552 | 611 | 326 | 414 | 470 | 414 | 414
OTH | 2213 | 1556.5 | 1768 | 1715 | 2650 | 2107 | 1697 | 1215 | 757
(blank) | 3521 | 3493.5 | 3630 | 2786 | 3036 | 3106 | 3177 | 2639 | 2171 | 1000 | 1000 | 1850
TS | 250 | 1000 | 1000 | 350 | 50 | 500 | 1000 | 1000 | 1000 | 1000 | 1000 | 1850
Grand Total | 7042 | 6987 | 7260 | 5572 | 6072 | 6212 | 6354 | 5278 | 4342 | 2000 | 2000 | 3700
CNC Lathe Machining
Row Labels | Sum of Jun-26 | Sum of Jul-26 | Sum of Aug-26 | Sum of Sep-26 | Sum of Oct-26 | Sum of Nov-26 | Sum of Dec-26 | Sum of Jan-27 | Sum of Feb-27 | Sum of Mar-27 | Sum of Apr-27 | Sum of May-27
Contract | 532 | 698 | 157 | 150 | 150 | 100 | 100 | 100
Group |  |  | 100 | 100 | 92 | 386 | 372 | 371 | 311
OTH | 2822 | 1001 | 2657 | 1904 | 2857 | 1458 | 607 |  |  |  | 150
(blank) | 4954 | 3299 | 4514 | 3754 | 4599 | 3444 | 2579 | 1971 | 1811 | 1236 | 2582 | 2432
TS | 1600 | 1600 | 1600 | 1600 | 1500 | 1500 | 1500 | 1500 | 1500 | 1236 | 2432 | 2432
Grand Total | 9908 | 6598 | 9028 | 7508 | 9198 | 6888 | 5158 | 3942 | 3622 | 2472 | 5164 | 4864
Total Machinig | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01
Contract | 1263 | 1308 | 467 | 260 | 160 | 185 | 110 | 110 | 0 | 0 | 0 | 0
Group | 327 | 327 | 652 | 711 | 418 | 800 | 842 | 785 | 725 | 0 | 0 | 0
OTH | 5035 | 2557.5 | 4425 | 3619 | 5507 | 3565 | 2304 | 1215 | 757 | 0 | 150 | 0
TS | 1850 | 2600 | 2600 | 1950 | 1550 | 2000 | 2500 | 2500 | 2500 | 2236 | 3432 | 4282

## Assembly
Row Labels | Sum of Jun-26 | Sum of Jul-26 | Sum of Aug-26 | Sum of Sep-26 | Sum of Oct-26 | Sum of Nov-26 | Sum of Dec-26 | Sum of Jan-27 | Sum of Feb-27 | Sum of Mar-27 | Sum of Apr-27 | Sum of May-27
Contract | 1180 | 1069 |  | 50 | 300 | 300 | 300 | 300 | 300 | 300
Group |  |  |  |  | 450 |  |  |  | 170 | 160
OTH | 3308 | 2224 | 1928 | 1754 | 2302 | 3775 | 4265 | 3090 | 1470 | 1060
(blank) | 5418 | 5533 | 5528 | 5604 | 5532 | 4775 | 4765 | 4160 | 2540 | 1620 | 100 | 100
IRON MAKING | 900 | 2200 | 3350 | 3500 | 2200 | 500 |  | 670 | 500
TS | 30 | 40 | 250 | 300 | 280 | 200 | 200 | 100 | 100 | 100 | 100 | 100
Grand Total | 10836 | 11066 | 11056 | 11208 | 11064 | 9550 | 9530 | 8320 | 5080 | 3240 | 200 | 200

## Plan Vs Actual (hidden)
S.No. | WBS/SO | Equipment Name | Planner | Category | Customer | Project Budget Value (INR) | MRM | MBOD | MBOS | BO/FIM (LLD) | MSC | LOG | Total Purchase Budget | MRM (Plate, Structural & Pipe) | MBOD ( Drawing Parts) | MBOS (Standard Parts) | FIM/LLD | MSC | Consumables | GGN BOOKED | Packing | Freight | Others (Bank service, Business Trip, Indirect Materail cost & Miscellaneous Expenses | Adjustment Cost | Total Material Cost | Fabrication |  | Machining -1 (SKODA+INNSE+GIANA+5 Axis) | Machining-2 (RD,UD & HMT) | Total | Assembly |  | Total Manufacturing Budget | Fabrication |  | Machining -1 (SKODA+INNSE+GIANA+ 5 Axis+VTL+HMC) | Machining-2 Others Machine | Total | Assembly |  | Adjustment Hours | Total Hours | Total Hours Cost | Total Manufacturing Cost 2022 ( A ) | Purchase Order Commitments ( B ) | Total EXP. Order Cost ( A+B) | Project Result | SCM Result | Manufacturing Result | Gross Margin %
[26 empty] | Hours | Budget | Hours | Hours | Budget | Hours | Budget |  | Hours | Cost | Hours | Hours | Cost | Hours | Cost | Cost
1 | A03141M220.21.20P0110 | Converter Oxygen Lance - 2 Nos | PRRR | WBS | HOA PHAT | 6091915 | 3293972 | 539981.6 | 163818.2 |  |  | 231527.8 | 4229299.6 | 4709722.5 | 774108.31 | 853077.46 |  | 12957.6 |  |  |  |  | 2124.5 |  | 6351990.37 | 998 | 691700 |  | 43 | 32600 |  |  | 724300 | 2008.45 | 1236788 |  | 18.8 | 4360 |  |  |  | 2027.25 | 1241148 | 7593138.37 | 97425.45 | 7690563.82 | -1598648.82 | -2122690.77 | -516848 | -26.24%
2 | A03141M220.22.20P0110 | Converter Oxygen Lance - 2 Nos | PRRR | WBS | HOA PHAT | 6091915 | 3293972 | 539981.6 | 163818.2 |  |  | 231527.8 | 4229299.6 | 3998416.38 | 387387.3 | 271518.49 |  | 64780.2 |  |  |  |  | 72474.88 | 3540052.92 | 4794577.25 | 998 | 691700 |  | 43 | 32600 |  |  | 724300 | 12.75 | 20073 | [6 empty] | 12.75 | 20073 | 4814650.25 | 32951.8 | 4847602.05 | 1244312.95 | -565277.65 | 704227 | 20.43%
3 | A03141M220.21.10.10P1150 | Lamella Suspension | JEAM01 | WBS | HOA PHAT | 12716649 | 4446345.1176 | 265376 | 918720 |  |  | 480505.6 | 6110946.7176 | 4464173.78 | 540989.44 | 90955.68 |  | 141771 | 143127.62 |  |  | 240000 | 100612.98 |  | 5721630.5 | 2491 | 1568439.2 | 736 | 120 | 3148800 | 500 | 600000 | 5317239.2 | 1954.59 | 1530916.2 | 406.9 | 366.3 | 2528415 | 413.5 | 496200 |  | 3141.29 | 4555531.2 | 10277161.7 | 312316.3 | 10589478 | 2127171 | 389316.2176 | 761708 | 16.73%
4 | A03141M220.40.10.40P1020 | GANTRY ASSEMBLY | SAHAXAVI | WBS | HOA PHAT | 7437380 | [6 empty] | 0 | -722649.92 | 2923877.07 | 735834.86 |  | 286884.7 | 73229.46 |  |  | 558000 | 125652.73 | -3714130 | 3980828.9 | 8800 |  | 430 |  |  | 550 |  | 0 | 2828.24 | 1628519 | 209.4 | 201.5 | 1073037.5 | 368.5 | 442200 | -312250 | 3607.64 | 3143756.5 | 7124585.4 | 201270 | 7325855.4 | 111524.6 | -3980828.9 | -3143756.5 | 1.5%
5 | A03332M610.60.20.30P1000 | Ladle Transport Car No.1 | RRAN | WBS | AURUBIS-USA | 9213198 | 1561587.3 | 1812655 | 39830 |  |  | 124594.9333 | 3538667.2333 | 1939236.86 | 1796301.88 | 141116.13 | 2648319.78 | 189070.34 | 2403.6 |  | 98375 | 97167 | 51006.09 | -33554.8181 | 6962996.68 | 1844 | 1224400 | 243.6667 | 50 | 1141333.3333 | 166.6667 | 200000 | 2565733.3333 | 2184.44 | 1253734 | 65.3 | 197.6 | 393872.5 | 256.5 | 307800 |  | 2703.84 | 1955406.5 | 8918403.18 | 36017.71 | 8954420.89 | 258777.11 | -3424329.4467 | 610326.8333 | 2.809%
6 | A03332M610.60.20.30P2000 | Ladle Transport Car No.2 | RRAN | WBS | AURUBIS-USA | 9213198 | 1561587.3 | 1812655 | 39830 |  |  | 124594.9333 | 3538667.2333 | 1615420.41 | 1796301.48 | 39006.08 | 2617950.62 | 450836.34 | 2878.89 |  | 98375 | 104166 | 44869.68 |  | 6769804.5 | 1844 | 1224400 | 243.6667 | 50 | 1141333.3333 | 166.6667 | 200000 | 2565733.3333 | 2166.74 | 1224677 | 38.5 | 19.4 | 211195 | 317 | 380400 |  | 2541.64 | 1816272 | 8586076.5 | 25219.29 | 8611295.79 | 601902.21 | -3231137.2667 | 749461.3333 | 6.533%
7 | A03332M610.60.20.30P3000 | Ladle Transport Car No.3 | RRAN | WBS | AURUBIS-USA | 9213198 | 1561587.3 | 1812655 | 39830 |  |  | 124594.9333 | 3538667.2333 | 1678745.12 | 1796301.28 | 44567.92 | 2618029.12 | 161591.32 | 2628.87 |  | 873881.39 | 96667 | 46670.16 |  | 7319082.18 | 1844 | 1224400 | 243.6667 | 50 | 1141333.3333 | 166.6667 | 200000 | 2565733.3333 | 2069.72 | 1228144 | 45.6 | 20.1 | 218455 |  |  |  | 2135.42 | 1446599 | 8765681.18 | 34587 | 8800268.18 | 412929.82 | -3780414.9467 | 1119134.3333 | 4.482%
8 | A03141M220.21.10.10P1050 | TRUNNION RING | ASDH01 | WBS | HOA PHAT | 59100000 | 20238237 | 14772200 |  |  | 5697500 | 4375600 | 45083537 | 18959805.82 | 44000 | 20247.38 | 14255242.26 | 4953186 | 1495.38 |  | 173258 | 3312425 | 1003041.56 | 448284.2686 | 42722701.4 | 19177 | 10685368 | 300 | 60 | 1189500 |  |  | 11874868 | 13175.715 | 9110413.5 | 106.4 | 43.8 | 692762.5 |  |  | -8325 | 13325.915 | 9803176 | 52525877.4 | 62832.8 | 52588710.2 | 6511289.8 | 2360835.6 | 2071692 | 11.02%
9 | A03307M220.40.10.10P1010 | LF ROOF | PADE | WBS | TATA-KPO | 4266421 | 1553396 | 7358 | 149404 |  | 42105 | 153220 | 1905483 | 1235754.05 | 131371.05 | 132373.97 | 510082.66 | 98729.3 |  |  |  | 67000 | 4502.32 |  | 2179813.35 | 2704 | 1561800 |  | 50 | 10000 |  |  | 1571800 | 3321.03 | 1941993.12 |  | 79 | 17775 |  |  |  | 3400.03 | 1959768.12 | 4139581.47 | 58909 | 4198490.47 | 67930.53 | -274330.35 | -387968.12 | 1.592%
10 | A03314M220.21.10.10P1000 | Convertor Vessel (Unit -1) | ASDH01 | WBS | AMNS-HAZIRA | 48336000 | 32125600 |  |  |  | 1834700 | 717600 | 34677900 | 33747495.63 |  | 310832.53 |  | 3214776.86 | 321234.13 |  |  | 3839758 | 851645.15 | 2472882.4838 | 42285742.3 | 12703.3333 | 7046300 |  | 130 | 72666.6667 |  |  | 7118966.6667 | 10585.05 | 6220659.8 | 17 | 30 | 118100 |  |  |  | 10632.05 | 6338759.8 | 48624502.1 | 18809.02 | 48643311.12 | -307311.12 | -7607842.3 | 780206.8667 | -0.6358%
11 | A03314M220.21.10.10P1010 | Lip Ring Segment 1 Nos | ASDH01 | WBS | AMNS-HAZIRA | 2555667 | 2014683.3333 | 0 | 266666.6667 |  |  | 90061.6667 | 2371411.6667 | 1686617.69 |  | 257220.01 | [6 empty] | 38876.76 |  | 1982714.46 | 27.6667 | 87900 | 21.3333 | 0 | 60800 |  |  | 148700 | 35.87 | 82619 | 51.6 |  | 337980 |  |  |  | 87.47 | 420599 | 2403313.46 |  | 2403313.46 | 152353.54 | 388697.2067 | -271899 | 5.961%
12 | A03080M221.20.10.10P1050 | Converter Trunnion Ring | ASDH01 | WBS | JSOL-ANGUL | 42685992 | 18908162 | 12684140 |  |  | 5630000 | 608800 | 37831102 | 17254657.85 | 159051.32 | 20424.01 |  | 5392590.3 | 210468.86 |  | 95450 | 765425 | 429452.08 | -931978.0926 | 24327519.42 | 17694 | 9815040 | 300 | 60 | 1189500 |  |  | 11004540 | 10164.877 | 7387354.5 | 171.5 | 180.5 | 1084795 |  |  |  | 10516.877 | 8472149.5 | 32799668.92 | 450000 | 33249668.92 | 9436323.08 | 13503582.58 | 2532390.5 | 22.11%
13 | A03080M221.20.10.10P1350 | Drive Side Trunnion Pin | ASDH01 | WBS | JSOL-ANGUL | 7423341 | [6 empty] | 0 | [11 empty] | 0 | [7 empty] | 0 | 2005 | 1050620 |  | 95.7 | 62205 |  |  | 62205 | 2100.7 | 1112825 | 1112825 |  | 1112825 | 6310516 | 0 | -1112825 | 85.01%
14 | A03080M221.20.10.10P1400 | Non drive side trunnion pin | ASDH01 | WBS | JSOL-ANGUL | 4840666 | [6 empty] | 0 | 2686776.81 | [8 empty] | 53735.54 | 2686776.81 | 2740512.35 | [7 empty] | 0 | 1999 | 1047476 | [6 empty] | 1999 | 1047476 | 3787988.35 |  | 3787988.35 | 1052677.65 | -2740512.35 | -1047476 | 21.75% | 6031770233
15 | C00593X010.1000 C00593X010.2000 C00593X010.3000 C00593X010.4000 | UNDER CARRIAGE BOTTOM PART | RRAN | DIRECT | TAKRAF | 11415816 | 3590130 | 1200000 | 184000 |  |  | 402272 | 5376402 | 4298689 | 12220 | 72656.31 | 0 | 384467.74 | 47836.99 |  | 0 | 0 | 7185.62 | -263686.32 | 4823055.66 | 4353 | 2888380 | 314 | 75 | 1585000 | 200 | 240000 | 4713380 | 6765.527 | 3779387.5 | 6.7 | 102.5 | 70338.75 |  |  | -2741200 | 6874.727 | 3849726.25 | 8672781.91 |  | 8672781.91 | 2743034.09 | 553346.34 | 863653.75 | 24.03%
16 | C00629X010.1000 | MANDREL THRUST BLOCK SPARE ITEMS | PRRR | DIRECT | SMS-BAHRAIN | 2042884.4 | [6 empty] | 0 |  | 120752 | 393724.2 |  |  |  |  | 12950 |  |  |  | 527426.2 | [7 empty] | 0 | [8 empty] | 0 | 0 | 527426.2 | 11261.6 | 538687.8 | 1504196.6 | -527426.2 | 0 | 73.63%
17 | C00594X010 C00595X010 | Bogies & Equalisers Service | RRAN | DIRECT | TAKRAF | 10446265.88 | 2000000 | 2000000 |  |  | 400000 | 150000 | 4550000 | 1670629.13 | 1368200.58 | 2169692.39 | 0 | 476620.3 | 232497.98 |  | 2480 | 0 | 12783.43 | -1643232.3375 | 5932903.81 | 2274.4 | 1515770.4 | 509.6 | 150 | 2454630.4 | 250 | 300000 | 4270400.8 | 3141.92 | 1871735 | 30.5 | 578.2 | 403732.5 |  |  | -4399100 | 3750.62 | 2275467.5 | 8208371.31 |  | 8208371.31 | 2237894.57 | -1382903.81 | 1994933.3 | 21.42%
18 | C00596X010.1000 C00596X010.2000 | Bogies & Equalisers Service | RRAN | DIRECT | TAKRAF | 2341667 | 982812 | 410905 |  |  | 200000 | 100000 | 1693717 | 954.24 |  |  |  | 5050 |  |  |  | 1200 | 4150 |  | 11354.24 | 568.6 | 378942.6 | 127.4 | 63 | 613657.6 | 100 | 120000 | 1112600.2 | 0.09 | 315 |  | 135.9 | 202335 | 504.5 | 605400 | 62335 | 640.49 | 808050 | 819404.24 |  | 819404.24 | 1522262.76 | 1682362.76 | 304550.2 | 65.01%
19 | C00683X010.1000 | LANTERN PINION SEGMENT | PRRR | DIRECT | HOA PHAT | 5753599.06 | 1056400 | 238080 |  |  |  | 150000 | 1444480 | 468194.73 | 461880 | 43493.36 |  |  | 14301.82 | [5 empty] | 987869.91 | 910 | 519000 | 160 | 50 | 1058000 | 64 | 76800 | 1653800 | 172.17 | 223368 | 90 | 52 | 604612.5 | 276 | 331200 |  | 590.17 | 1159180.5 | 2147050.41 | 181830.9 | 2328881.31 | 3424717.75 | 456610.09 | 494619.5 | 59.52%
20 | C00630X010.1000 | HOUSING & BEARING ASSEMBLY (IS12/450) | JEAM01 | DIRECT | VOITH | 12916000 | 3950000 | 2212382 | 664200 |  |  | 65000 | 6891582 | 5838669.09 | 1164715 | 736251.8 |  | 219864.2 | 176737.24 |  |  |  | 293.28 | -31983.12 | 8136530.61 | 3080 | 1889600 | 200 | 894.5455 | 1210818.1818 | 600 | 720000 | 3820418.1818 | 3407.003 | 1991712 | 142.9 | 957.9 | 1122548.5 | 114.5 | 137400 | -2934205 | 4622.303 | 3251660.5 | 11388191.11 | 50775.06 | 11438966.17 | 1477033.83 | -1244948.61 | 568757.6818 | 11.44%
21 | C00656X010.1000 | TUNDISH | SAHAXAVI | DIRECT | SMS Concast AG | 8401287.61 | 3132000 |  |  |  |  | 830000 | 3962000 | 1769990.92 |  | 23029.9 |  | 206874 | 3791.01 |  |  | 225000 | 36955.92 | -1100000 | 2265641.75 | 3715 | 2210250 | 30 | 120 | 174000 |  |  | 2384250 | 4053.05 | 2266976 | 155 | 190.2 | 555670 |  |  | 465000 | 4398.25 | 2822646 | 5088287.75 | 400000 | 5488287.75 | 2912999.86 | 1696358.25 | -438396 | 34.67%
22 | C00686X010.1000 | TIGHTENER DISC SPRING 763 MM | RRAN | DIRECT | PAUL WURTH-LUXEMBOURG | 816423.81 |  | 504000 | 168000 |  |  | 12000 | 684000 |  | 546000 | 284651.33 | [6 empty] | 10920 |  | 841571.33 | [7 empty] | 0 | 5 | 15325 | [6 empty] | 5 | 15325 | 856896.33 |  | 856896.33 | -40472.52 | -157571.33 | -15325 | -4.957%
23 | C00687X010.3000 | Segment 8 | RRAN | DIRECT | TATA-KPO | 2750000 | [6 empty] | 0 | 31912.09 | 965.79 |  |  | 2500 |  |  |  |  | 707.56 |  | 36085.44 |  |  | 172.5 | 112 | 901300 | 900 | 1080000 | 1981300 | 69.29 | 242665 |  |  |  | 791.5 | 949800 |  | 860.79 | 1192465 | 1228550.44 | 110000 | 1338550.44 | 1411449.56 | -36085.44 | 788835 | 51.33%
24 | ET470089284-72004880 | UPPER SELING RING COMPONENTS | GOKR | SERVICE | TATA-KPO | 789000 | [6 empty] | 0 | 274122.88 |  | 241971.15 |  |  |  | 4166.44 |  | 30000 |  |  | 550260.47 | [8 empty] | 116.5 | 143100.4 |  |  |  | 279 | 334800 |  | 395.5 | 477900.4 | 1028160.87 | 11137.78 | 1039298.65 | -246132.21 | -550260.47 | -477900.4 | -31.2%
25 | ET430076201-72004060 | ADJUSTABLE SKIRT & COOLING RING | PADE | SERVICE | TATA-JSR | 2195296 | 567031 | 15018 | 209902 |  | 222580 | 184870 | 1199401 | 962327.02 | 66902.66 | 330310.26 |  | 426163.03 |  | 56196.67 |  | 110000 |  | -346600.8 | 1951899.64 | [8 empty] | 420 | 264480 | [5 empty] | 180000 | 420 | 264480 | 2216379.64 | 16650.5 | 2233030.14 | 18462.53 | -752498.64 | -264480 | 0.841%
26 | ET470089468-72004894 | FLUX CHUTES | PADE | SERVICE | TATA-NINL | 819000 | [6 empty] | 0 | 116544.53 |  | 9666.53 |  | 850 |  | 22924.22 |  |  |  |  | 149985.28 | [8 empty] | 826 | 644168 | [5 empty] | 480088 | 826 | 644168 | 794153.28 | 945 | 795098.28 | 46825.94 | -149985.28 | -644168 | 5.717%
GRAND TOTAL | [5 empty] | 289872779.76 | 105837502.3509 | 40827387.2 | 3008019.0667 | 0 | 14026885 | 9156769.6667 | 172856563.2843 | 108686206.61 | 14091325.16 | 7222621.75 | 22649624.44 | 16689563.23 | 1232631.85 | 83287.33 | 1354769.39 | 9446808 | 2897660.24 | 1082830.9941 | 184354498 | 86026 | 45223390.2 | 4031.8333 | 2120.5455 | 17157872.8485 | 3664 | 3736800 | 66118063.0485 | 73488.022 | 46407219.02 | 1537.3 | 3269.4 | 9702189.75 | 3321 | 3985200 | -9145452 | 81615.722 | 60094608.77 | 244449106.77 | 2112939.21 | 246562045.98 | 43394021.11 | -11497934.7157 | 6023454.2785
.